## Admin Dashboard1
POWER SYSTEM DEVLOPMENT FUND (PSDF)
Summary Status of the schemes submitted by the entities for funding from PSDF
Status as on 31-01-2021 All figures in Rupees Crore
Sr. No. | Name of the entity (Figures in the bracket indicate estimated cost of the scheme) | Total number of the scheme | Estimated cost of the schemes | Estimated cost accepted | Grant Approved
Format D1 | Proposala approved by Monitoring Committee: | 160 | 21447.5027 | 17174.79 | 11650.95
Format D2 | Proposals recommended by the Appraisal Committee: | 14 | 902.54 | 579.67
Format D3 | Proposals regarding installation of capacitors: | 2 | 398.45
Format D4/1 | Proposals under process of examination by the sub group | 22 | 1674.29
Format D4/2 | Proposals received recently: | 15 | 1087.22
Format D5 | Proposals not eligible for funding from PSDF / Deemed Return: | 93 | 21594.6667
| Total | 306 | 47104.6694 | 17754.46 | 11650.95
Chandigarh, D&D, DNH yet to submit the schemes.
Note on B5: Author: Click to go to the Admin Dashboar -2 (Details Project ststus of approved projects)

## Project Dashboard
STATUS OF PROJECTS DASHBOARD
Entity Name: ________________
Project Approved and under Execution
Sr.no | Projct ID | Name of Proposal | Category | DPR Cost | Grant Approved | Date of sanction | Grant released | % of Grant Untilised | Comletion Period | Schedule completion date | 1st Time Extention | 2nd Time Extention | 3rd Time Extention
Projects under for Examination
Sr.no | Projct ID | Name of Proposal | Category | DPR Cost | submission Date | Status of examination (Under Examination / cleared/Declined) |  |  | date of Sanction / Decline
[6 empty] | TESG | App. Co | Mo. Co
NEW Projects pending for acceptance
Sr.no | Projct ID | Name of Proposal | category | DPR Cost | submission Date | Accepted Yes/No
Projects completed
Sr.no | Projct ID | Name of Proposal | category | DPR Cost | Grant Approved | Grant released | % of Grant Untilised | Comletion Period | Schedule completion date | Actual completion date
Projects Declined
Sr.no | Projct ID | Name of Proposal | category | DPR Cost | Date of Decline
ENTITY BUDGET DASHBOARD
[5 empty] | RE FY 2020-21 |  |  |  |  | RE FY 2020-21
Sr.no | Projct ID | Name of Proposal | Grant Approved | Cumulative Grant disbusred | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
Total
ENTITY PAYMENT DASHBOARD
Sr.no | Projct ID | Name of Proposal | Grant Approved | Payment released
|  |  |  | 10% stg-1 | 20% stg-2 | 60% stg-3 | 10% stg-4 | Total
1
2
3
ENTITY OUTPUT OUTCOME DASHBOARD
Date : 08.01.2021
OUTPUTS 2021-22 | [10 empty] | OUTCOMES 2021-22
Output | Indicator (s) | Annual | Target 2021-22 |  |  |  | Progress 2021-22 |  |  |  | Outcome | Indicator (s) | Annual | Target 2021-22 |  |  |  | Progress 2021-22
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1. Enhanced execution of projects to bring improvement in grid safety and operation | 1.1.Total length of transmission line renovated and modernized (CKMs) | [9 empty] | 1. Improvement in grid safety and operation | 1.1.Increase in power transmission capacity (MVA) | bar: Progress 2021-22 Q1
| 1.1.Addition in reactive power capacity available to control voltage profile (MVAR) | [10 empty] | 1.1. Total number of substations rectified for discrepancies
1.2.Number of substations renovated and upgraded
1.3.Number of Special Energy Meters (SEM) and Phaser Measurement Units (PMUs) installed
1.4.Amount of fund utilized on approved projects (Crore)
Note on C54: Author: click the Project ID to open payment processing mdule

## Admin Dashboard-2
POWER SYSTEM DEVELOPMENT FUND(PSDF) | [24 empty] | Disbursed | 4185.2826 |  |  | Disbursed | 1293.6583 |  | Disbursed | 57.1278 | 25.764
[25 empty] | Balance | #REF! |  |  | Balance | #REF! |  | Balance | #REF! | #REF!
Status as on 31-01-2021 Format D-1:Proposals approved under PSDF All figures in Rs Crore | [23 empty] | Cumulative Grant disbursed up to 31.3.2018 | Grant disbursed during FY 2018-19 |  |  | Cumulative Grant disbusred up to 31.3.2019 | Grant disbursed during FY 2019-20 |  |  | Cumulative Grant disbusred up to 31.3.2020 | Grant disbursed during FY 2020-21 |  |  | Cumulative Grant disbusred up to 30.6.2020
Project ID | Name of State/Entity | Region | Name of Entity | Name of Scheme and Unique ID No | Date of Submission of Scheme by Entity | Estimated cost by entity | Date of Techno- Economic clearance | Date of Recommendation by Appraisal Committee | Project Cost accepted by Appraisal Committee. | Category of Funding | Quantum of Funding Recommended by Appraisal Committee | Date of Concurrence by CERC. | Grant Approved by Monitoring Committee | Date of Approval by Monitoring Committee | Date of Issuance of sanction order by MoP | Date of Signing of Agreement | Completion schedule (in Month) | Date of release of first Installment | Proposed Completion date as per release of first Installment | Time Extention 1st | Time Extention 2nd | Time Extention 3rd | Time Extention 4th |  | GBS | EBR | Total |  | GBS | EBR | Total |  | GBS | EBR | Total
I | II |  | III | IV | V | VI | VII | VIII | IX | X | XI | XII | XIII | XIV | XV | XVI | [7 empty] | 6 | 7 | 8 | 9=7+8 | 10=6+9 | 11 | 12 | 13=11+12 | 14=10+13 | 15 | 16 | 17=15+16 | 18=14+17
1 | POWERGRID | Central | POWERGRID | URTDSM Scheme (Installation of PMUs (001) | 2014-06-23 | 374.63 | 2014-08-27 | 2014-08-29 | 374.63 | 5.1 (c ) | 70 | 2014-10-07 | 262.24 | 2014-10-08 | 2014-12-31 | 2015-02-27 | 27 | 2015-10-29 | 2018-01-29 |  |  |  |  | 44.9808 | 1.8392 | 25.34 | 27.1792 | 72.16 |  | 9.957 | 9.957 | 82.117 |  |  | 0 | 82.117
2 | Kerala | SR | KSEBL | Renovation and Upgradation of protection system of substations (002) | 2014-07-30 | 97.9 | 2014-08-25 | 2014-08-29 | 91.46 | 5.1 (c ) | 90 | 2014-10-07 | 82.31 | 2014-10-08 | 2014-12-31 | 2015-02-20 | 18 | 2016-01-28 | 2017-07-28 |  |  |  |  | 13.63 | 1.22 |  | 1.22 | 14.85 |  | 0 | 0 | 14.85 |  |  | 0 | 14.85
3 | Rajasthan | NR | RRVPNL | Renovation and Upgradation of protection system of substations (003) | 2014-06-18 | 159.53 | 2014-08-25 | 2014-08-29 | 159.53 | 5.1 (c ) | 90 | 2014-10-07 | 143.58 | 2014-10-08 | 2014-12-31 | 2015-02-06 | 24 | 2016-03-31 | 2018-03-31 |  |  |  |  | 6.4449 | 12.8851 |  | 12.8851 | 19.33 |  | 0 | 0 | 19.33 |  |  | 0 | 19.33
4 | Rajasthan | NR | RRVPNL | Installation of Bus Reactors (005) | 2014-06-18 | 23.96 | 2014-08-25 | 2014-08-29 | 23.87 | 5.1(b ) | 90 | 2014-10-07 | 21.48 | 2014-10-08 | 2014-12-31 | 2015-02-06 | 18 | 2016-03-22 | 2017-09-22 |  |  |  |  | 18.252 | 19.488 |  | 19.488 | 37.74 |  | 8.3646 | 8.3646 | 46.1046 |  |  | 0 | 46.1046
5 | West Bengal | ER | WBSETCL | Renovation and Upgradation of protection system of substations (007) | 2014-07-30 | 136.45 | 2014-08-25 | 2014-08-29 | 120.67 | 5.1 (c ) | 90 | 2014-10-07 | 108.6 | 2014-10-08 | 2014-12-31 | 2015-02-10 | 15 | 2016-02-04 | 2017-05-04 |  |  |  |  | 38.677 | 0 | 7.945 | 7.945 | 46.622 |  | 0 | 0 | 46.622 |  |  | 0 | 46.622
6 | Odisha | ER | OPTCL | Renovation and Upgradation of protection system of substaions (008) | 2014-07-17 | 184.19 | 2014-11-24 | 2014-11-25 | 180.56 | 5.1 (c ) | 90 | 2015-01-12 | 162.5 | 2015-03-19 | 2015-05-11 | 2015-08-05 | 24 | 2016-03-22 | 2018-03-22 |  |  |  |  | 52.465 | 35.825 | 33.806 | 69.631 | 122.096 |  | 27.438 | 27.438 | 149.534 |  |  | 0 | 149.534
7 | Assam | NER | AEGCL | Renovation and Upgradation of protection system of substations(011) | 2014-08-21 | 382.48 | 2014-11-24 | 2014-11-25 | 299.37 | 5.1 (c ) | 100 | 2015-01-12 | 299.37 | 2015-03-19 | 2015-05-11 | 2016-02-29 | 18 | 2016-03-31 | 2017-09-30 |  |  |  |  | 8.717 | 0.003 | 0.977 | 0.98 | 9.697 |  | 0 | 0 | 9.697 |  |  | 0 | 9.697
8 | Karnataka | SR | KPCL | Renovation and Upgradation of protection system of substations (015) | 2014-09-11 | 26.93 | 2014-11-24 | 2014-11-25 | 19.84 | 5.1 (c ) | 90 | 2015-02-24 | 17.85 | 2015-03-19 | 2015-05-11 | 2015-06-12 | 24 | 2016-02-04 | 2018-02-04 |  |  |  |  | 32.904 | -0.004 |  | -0.004 | 32.9 |  | 0 | 0 | 32.9 |  |  | 0 | 32.9
9 | Nagaland | NER | DOP, Nagaland | Renovation and Upgradation of protection system of substations (017) | 2014-09-17 | 39.96 | 2014-11-24 | 2014-11-25 | 39.96 | 5.1 (c ) | 100 | 2015-01-12 | 39.96 | 2015-03-19 | 2015-05-11 | 2015-08-17 | 18 | 2016-03-08 | 2017-09-08 |  |  |  |  | 56.04 | 0 |  | 0 | 56.04 |  | 0 | 0 | 56.04 |  |  | 0 | 56.04
10 | Bihar | ER | BSPTCL | Renovation and Upgradation of protection system of substations (018) | 2014-09-18 | 74.13 | 2014-12-19 | 2015-01-14 | 71.35 | 5.1 (c ) | 90 | 2015-03-18 | 64.22 | 2015-03-19 | 2015-05-11 | 2015-12-03 | 24 | 2016-05-16 | 2018-05-16 |  |  |  |  | 29.77 | 0 | 2.647 | 2.647 | 32.417 |  | 0 | 0 | 32.417 |  |  | 0 | 32.417
11 | Uttar Pradesh | NR | UPPTCL | Installation of Capacitors and FSC. (025) | 2014-11-02 | 176.5 | 2015-01-13 | 2015-01-14 | 39.29 | 5.1(b) | 90 | 2015-03-18 | 35.36 | 2015-03-19 | 2015-05-11 | 2015-11-26 | 18 | 2016-03-08 | 2017-09-08 |  |  |  |  | 40.705 | 48.765 |  | 48.765 | 89.47 |  | 20.5 | 20.5 | 109.97 |  |  | 0 | 109.97
12 | Uttar Pradesh | NR | UPPTCL | Renovation and Upgradation of protection system of substations. (026) | 2014-11-02 | 279.19 | 2015-01-13 | 2015-01-14 | 202.94 | 5.1 (c ) | 90 | 2015-03-18 | 182.65 | 2015-03-19 | 2015-05-11 | 2015-11-26 | 18 | 2016-03-31 | 2017-09-30 |  |  |  |  | 1.5 | 0 |  | 0 | 1.5 |  | 0 | 0 | 1.5 |  |  | 0 | 1.5
13 | Gujarat | WR | GETCO | Automatic Demand Management Scheme. (034) | 2015-01-01 | 1.72 | 2015-01-12 | 2015-01-14 | 1.67 | 5.1 (c ) | 90 | 2015-03-18 | 1.5 | 2015-03-19 | 2015-05-11 | 2015-08-23 | 3 | 2016-01-18 | 2016-04-18 |  |  |  |  | 23.0848 | 0.0052 | 50.896 | 50.9012 | 73.986 |  | 6.536 | 6.536 | 80.522 | 0.592 |  | 0.592 | 81.114
14 | Tamil Nadu | SR | TANTRANSCO | Renovation and Upgradation of protection system of substations (020) | 2014-10-03 | 202 | 2015-02-25 | 2015-03-12 | 138.28 | 5.1 (c ) | 90 | 2015-05-28 | 124.45 | 2015-07-14 | 2015-08-04 | 2016-01-29 | 36 | 2016-11-25 | 2019-11-25 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0.37 | 0.37 | 0.37 |  |  | 0 | 0.37
15 | Gujarat | WR | GETCO | Load Forecasting Scheme (035) | 2015-01-03 | 3.7 | 2015-02-25 | 2015-03-12 | 3.7 | 5.1 (e) | 100 | 2015-05-28 | 3.7 | 2015-07-14 | 2015-08-04 | 2016-02-24 | 3 | 2019-11-06 | 2020-02-06 |  |  |  |  | 0.95 | 0 |  | 0 | 0.95 |  | 3.45 | 3.45 | 4.4 |  |  | 0 | 4.4
16 | Puducherry | SR | DoP, Puducherry | Renovation and Upgradation of protection system of substations (021) | 2014-10-10 | 13.98 | 2015-03-03 | 2015-03-12 | 10.56 | 5.1 (c ) | 90 | 2015-05-28 | 9.5 | 2015-07-14 | 2015-08-04 | 2016-02-26 | 12 | 2017-05-18 | 2018-05-18 |  |  |  |  | 13.078 | 31.132 | 6.146 | 37.278 | 50.356 |  | 13.88 | 13.88 | 64.236 |  |  | 0 | 64.236
17 | Meghalaya | NER | MePTCL | Renovation and Upgardation of protection system of substations (042) | 2015-02-22 | 102.8 | 2015-03-03 | 2015-03-12 | 69.19 | 5.1 (c ) | 100 | 2015-05-28 | 69.19 | 2015-07-14 | 2015-08-04 | 2016-03-08 | 18 | 2016-07-20 | 2018-01-20 |  |  |  |  | 4.495 | -0.005 |  | -0.005 | 4.49 |  | 0 | 0 | 4.49 |  |  | 0 | 4.49
18 | NRPC | NR | NRPC | Study Program on the integration of renewable energy resources (054) | 2015-05-15 | 6.45 | 2015-05-19 | 2015-06-10 | 6.45 | 5.1 (e) | 100 | 2015-08-25 | 6.45 | 2015-10-01 | 2015-10-28 | 2015-11-24 | 3 | 2015-12-29 | 2016-03-29 |  |  |  |  | 10.11 | 2.18 | 0.562 | 2.742 | 12.852 |  | 22.358 | 22.358 | 35.21 |  |  | 0 | 35.21
19 | Telangana | SR | TSTRANSCO | Renovation and Upgradation of protection system of substations. (016) | 2014-09-08 | 72.6 | 2015-05-19 | 2015-06-10 | 59.97 | 5.1(c) | 90 | 2015-08-25 | 53.97 | 2015-10-01 | 2015-10-28 | 2016-02-01 | 17 | 2016-05-16 | 2017-10-16 |  |  |  |  | 18.666 | 0.004 | 5.962 | 5.966 | 24.632 |  | 0 | 0 | 24.632 |  |  | 0 | 24.632
20 | Assam | NER | AEGCL | Installation of BCU. (047) | 2015-01-07 | 57.13 | 2015-02-25 | 2015-06-10 | 53.52 | 5.1(c) | 100 | 2015-08-25 | 53.52 | 2015-10-01 | 2015-10-28 | 2016-02-29 | 18 | 2016-11-25 | 2018-05-25 |  |  |  |  | 2.684 | 5.316 | 15.8673 | 21.1833 | 23.8673 |  | 0 | 0 | 23.8673 |  |  | 0 | 23.8673
21 | Mizoram | NER | DoP, Mizoram (032) | Renovation and Upgardation of protection system of substations. (32) | 2014-12-01 | 31.38 | 2015-05-06 | 2015-06-10 | 26.84 | 5.1(c ) | 100 | 2015-08-25 | 26.84 | 2015-10-01 | 2015-10-28 | 2016-04-26 | 18 | 2016-11-29 | 2018-05-29 |  |  |  |  | 26.4115 | -0.0015 | 37.08 | 37.0785 | 63.49 |  | 0 | 0 | 63.49 |  |  | 0 | 63.49
22 | Jammu & Kashmir | NR | PDD-J&K | Renovation and Upgradation of protection system of substations in Jammu(023) | 2014-11-14 | 182.44 | 2014-12-19 | 2015-06-10 | 140.04 | 5.1(c ) | 100 | 2015-08-05 | 140.04 | 2015-10-01 | 2015-10-28 | 2016-04-05 | 18 | 2017-07-14 | 2019-01-14 |  |  |  |  | 5.549 | 10.191 | 9.901 | 20.092 | 25.641 |  | 2.96 | 2.96 | 28.601 |  |  | 0 | 28.601
23 | Meghalaya | NER | MePGCL | Renovation and upgradation of Protection and Contro;l System. (57) | 2015-05-12 | 41.93 | 2015-07-27 | 2015-09-08 | 32.53 | 5.1(c ) | 100 | 2015-11-03 | 32.53 | 2015-12-15 | 2016-01-05 | 2016-06-10 | 18 | 2016-11-25 | 2018-05-25 |  |  |  |  | 8.85 | 17.25 |  | 17.25 | 26.1 |  | 0 | 0 | 26.1 |  |  | 0 | 26.1
24 | Tripura | NER | TSEBL | Renovation and Upgradation of Protection System (040) | 2015-02-22 | 79.95 | 27-07-2015 | 2015-09-08 | 31.05 | 5.1(C ) | 100 | 2015-11-03 | 31.05 | 2015-12-15 | 2016-01-05 | 2016-03-30 | 18 | 2017-01-09 | 2018-07-09 |  |  |  |  | 34.444 | -0.004 | 3.179 | 3.175 | 37.619 |  | 0.64 | 0.64 | 38.259 | 5.6209 |  | 5.6209 | 43.8799
25 | Himachal Pradesh | NR | HPSEBL | Renovation and Upgradation of Protection System (048) | 2015-03-27 | 68.59 | 2015-07-03 | 2015-09-08 | 55.44 | 5.1(C ) | 100 | 2015-11-03 | 55.44 | 2015-12-15 | 2016-01-05 | 2016-06-08 | 18 | 2017-05-31 | 2018-11-30 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 96.541 | 96.541 | 96.541 |  |  | 0 | 96.541
26 | POWERGRID | ER | POWERGRID | Installation of STATCOMs in ER at Ranchi-New, Rourkela, Kishanganj and Jeypore substations of POWERGRID (056) | 2015-06-05 | 1059.5 | 2015-07-27 | 2015-09-08 | 700.31 | 5.1(b) | 90 | 2015-11-03 | 630.28 | 2015-12-15 | 2016-01-05 | 2016-09-29 | 30 | 2017-03-31 | 2019-09-30 |  |  |  |  | 18.122 | 18.128 | 18.125 | 36.253 | 54.375 |  | 0 | 0 | 54.375 |  |  | 0 | 54.375
27 | Jammu & Kashmir | NR | PDD-J&K | Renovation and Upgradation of protection system of substations in Kashmir(024) | 2014-11-14 | 193.03 | 2014-12-19 | 14-01-2015 10-06-2015 | 146.12 | 5.1 (c ) | 100 | 2016-02-10 | 146.12 | 2016-02-22 | 2016-03-17 | 2016-04-22 | 18 | 2019-06-06 | 2020-12-06 |  |  |  |  | 11.34 | 9.41 | 28.248 | 37.658 | 48.998 |  | 8.05 | 8.05 | 57.048 |  |  | 0 | 57.048
28 | Karnataka | SR | KPTCL | Renovation and Upgradation of protection system of substations (12) | 2014-08-26 | 77.46 | 2015-09-28 | 2015-11-17 | 67.13 | 5.1(C) | 90 | 2015-12-16 | 60.42 | 2016-02-22 | 2016-03-17 | 2016-05-12 | 12 | 2017-03-31 | 2018-03-31 |  |  |  |  | 101.7519 | -0.0019 |  | -0.0019 | 101.75 |  | 9.69 | 9.69 | 111.44 |  |  | 0 | 111.44
29 | Delhi | NR | DTL | Renovation and Upgradation of Protection System.(049) | 2015-03-24 | 125.98 | 2015-10-16 | 2015-11-17 | 125.98 | 5.1(c) | 90 | 2016-02-10 | 113.38 | 2016-02-22 | 2016-03-17 | 2016-05-04 | 27 | 2016-11-25 | 2019-02-25 |  |  |  |  | 0 | 0 | 1.639 | 1.639 | 1.639 |  | 2.487 | 2.487 | 4.126 |  |  | 0 | 4.126
30 | Uttrakhand | NR | PTCUL | Renovation and Upgradation of Protection System.(051) | 2015-04-09 | 127.11 | 2015-10-16 | 2015-11-17 | 125.05 | 5.1(c) | 100 | 2016-01-14 | 125.05 | 2016-02-22 | 2016-03-17 | 2016-06-08 | 18 | 2016-11-08 | 2018-05-08 |  |  |  |  | 21.031 | 31.899 |  | 31.899 | 52.93 |  | 0 | 0 | 52.93 |  |  | 0 | 52.93
31 | Punjab | NR | PSTCL | Bus bar protection (052) | 2015-03-16 | 18.21 | 2015-09-28 | 2015-11-17 | 18.21 | 5.1(c) | 90 | 2016-01-14 | 16.39 | 2016-02-22 | 2016-03-17 | 2016-12-29 | 18 | 2019-03-27 | 2020-09-27 |  |  |  |  | 2.44 | 0 |  | 0 | 2.44 |  | 0 | 0 | 2.44 |  |  | 0 | 2.44
32 | Madhya Pradesh | WR | MPPTCL | Renovation and Upgradation of protection system of substations (28) | 2014-11-25 | 173 | 4-11-2015 | 2015-11-17 | 103 | 5.1(C) | 90 | 2016-01-14 | 92.7 | 2016-02-22 | 2016-03-17 | 2016-06-22 | 24 | 2017-03-31 | 2019-03-31 |  |  |  |  | 0.32 | 0 | 0.488 | 0.488 | 0.808 |  | 0 | 0 | 0.808 |  |  | 0 | 0.808
33 | Madhya Pradesh | WR | MP SLDC | Implementation of Integrated system for ABT Open Access and MIS for MPSLDC (061) | 2015-08-01 | 4 | 2015-09-28 | 2015-11-17 | 4 | 5.1(c) | 90 | 2016-01-14 | 3.6 | 2016-02-22 | 2016-03-17 | 2016-06-22 | 12 | 2017-05-17 | 2018-05-17 |  |  |  |  | 14.829 | 0.001 |  | 0.001 | 14.83 |  | 0 | 0 | 14.83 |  |  | 0 | 14.83
34 | Gujarat | WR | GETCO | Wind Generation forecasting for state of Gujarat(58) | 2015-07-06 | 1.62 | 2015-09-28 | 2015-11-17 | 1.62 | 5.1(e) | 100 | 2016-01-14 | 1.62 | 2016-02-22 | 2016-03-17 | 2016-12-05 | 36 | 2017-06-27 | 2020-06-27 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
35 | ERPC | ER | ERPC | Creation and Maintenance of web based protection database management (067) | 2015-09-24 | 20 | 2015-11-04 | 2015-11-17 | 20 | 5.1(e) | 100 | 2016-01-14 | 20 | 2016-02-22 | 2016-03-17 | 2016-04-26 | 18 | 2016-06-28 | 2017-12-28 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 7.53 | 7.53 | 7.53 |  |  | 0 | 7.53
36 | Uttar Pradesh | NR | UPPTCL | Reconductoring of existing line by HTLS conductor for relieving congestion. (027) | 2014-11-02 | 80 | 2015-09-28 | 2015-11-17 | 80 | 5.1(d) | 75 | 2016-01-14 | 60 | 2016-02-22 | 2016-03-17 | Scheme withdrawn | 18 | [6 empty] | 0.559 | 0.001 | 1.118 | 1.119 | 1.678 |  | 3.35 | 3.35 | 5.028 |  |  | 0 | 5.028
37 | Chhattisgarh | WR | CSPTCL | Renovation and Upgradation of protection system. (039) | 2015-01-06 | 176.63 | 2015-10-16 | 2016-03-08 | 68.52 | 5.1 (c ) | 90 | 2016-07-12 | 61.67 | 2016-08-19 | 2016-09-05 | 2019-03-12 | 12 | 2019-06-25 | 2020-06-25 |  |  |  |  | 36.98 | 0.01 | 0.182 | 0.192 | 37.172 |  | 9.9437 | 9.9437 | 47.1157 |  |  | 0 | 47.1157
38 | Madhya Pradesh | WR | MPPGCL | Installation of 125MVAR Bus Reactor at SSTPP Khandwa substation of MPPGCL (062) | 2015-08-24 | 18.85 | 2016-01-07 | 2016-03-08 | 6.21 | 5.1(b) | 90 | 2016-07-12 | 5.59 | 2016-08-19 | 2016-09-05 | 2016-12-29 | 12 | 2017-05-18 | 2018-05-18 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 2.48 | 2.48 | 2.48 | 0.7 |  | 0.7 | 3.18
39 | Telangana | SR | TSTRANSCO | Installation of 5 nos. of 125MVAR at 400kV Mahaboobnagar, Mamidipally, Malkaram, Gajwel and Shankarpalli (059) | 2015-07-07 | 53.63 | 2016-01-07 | 2016-03-08 | 53.63 | 5.1(b) | 90 | 2016-07-12 | 48.27 | 2016-08-19 | 2016-09-05 | 2016-11-21 | 12 | 2017-05-17 | 2018-05-17 |  |  |  |  | 3.35 | 0.51 | 6.7 | 7.21 | 10.56 |  | 19.59 | 19.59 | 30.15 |  |  | 0 | 30.15
40 | Arunachal Pradesh | NER | APPCL | Renovation and Upgradation of Protection System. (044) | 2015-02-24 | 33.45 | 2016-01-08 | 2016-03-08 | 18.21 | 5.1 (c ) | 100 | 2016-07-12 | 18.21 | 2016-08-19 | 2016-09-05 | 2019-09-27 | 18 | 2019-11-05 | 2021-05-05 |  |  |  |  | 4.711 | 4.299 | 1.889 | 6.188 | 10.899 |  | 18.57 | 18.57 | 29.469 |  |  | 0 | 29.469
41 | Manipur | NER | MSPCL | Renovation and Upgradation of Grid Substation of MSPCL (055) | 2015-03-10 | 33.5 | 2016-01-08 | 2016-03-08 | 33.5 | 5.1 (c ) | 100 | 2016-07-12 | 33.5 | 2016-08-19 | 2016-09-05 | 2017-11-09 | 18 | 2018-03-27 | 2019-09-27 |  |  |  |  | 3.99 | 3.09 | 11.4086 | 14.4986 | 18.4886 |  | 9.717 | 9.717 | 28.2056 |  |  | 0 | 28.2056
42 | Madhya Pradesh | WR | MPPGCL | Renovation and Upgradation of protection system of substations.(029) | 2014-11-25 | 88.5 | 2015-07-03 | 2016-03-08 | 52.34 | 5.1 (c ) | 90 | 2016-07-12 | 47.11 | 2016-08-19 | 2016-09-05 | 2016-10-04 | 18 | 2017-03-31 | 2018-09-30 |  |  |  |  | 11.27 | 11.2 | 33.542 | 44.742 | 56.012 |  | 31.405 | 31.405 | 87.417 |  |  | 0 | 87.417
43 | Andhra Pradesh | SR | APGENCO | Renovation and Upgradation of protection system of substations (010) | 2014-08-13 | 40.12 | 2015-10-16 | 2016-03-08 | 44.42 | 5.1 (c ) | 90 | 2016-07-12 | 39.98 | 2016-08-19 | 2016-09-05 | 2016-11-24 | 24 | 2017-03-31 | 2019-03-31 |  |  |  |  | 2.348 | 0.002 | 4.696 | 4.698 | 7.046 |  | 14.09 | 14.09 | 21.136 |  |  | 0 | 21.136
44 | Andhra Pradesh | SR | APTRANSCO | Renovation and Upgradation of protection system of substations(009) | 2014-08-07 | 106.32 | 2015-10-16 | 2016-03-08 | 125.27 | 5.1 (c ) | 90 | 2016-07-12 | 112.74 | 2016-08-19 | 2016-09-05 | 2016-11-23 | 24 | 2017-04-03 | 2019-04-03 |  |  |  |  | 0 | 0 | 5.664 | 5.664 | 5.664 |  | 11.326 | 11.326 | 16.99 |  |  | 0 | 16.99
45 | West Bengal | ER | WBPDCL | Renovation and Modernization of 220/ 132 kV STPS switch yard and implementation of Substaion Automation System.(072) | 2015-12-23 | 28.5 | 2016-05-06 | 2016-05-31 | 26.09 | 5.1 (c ) | 90 | 2016-08-05 | 23.48 | 2016-08-19 | 2016-09-05 | 2016-12-29 | 18 | 2017-05-18 | 2018-11-18 |  |  |  |  | 9.45 | 18.9 |  | 18.9 | 28.35 |  | 56.71 | 56.71 | 85.06 |  |  | 0 | 85.06
46 | Bihar | ER | BSPTCL | Installation of Capacitor bank in 20 Nos of Grid Sub Station (074) | 2016-09-01 | 24.96 | 2016-05-06 | 2016-05-31 | 20.98 | 5.1(b) | 90 | 2016-08-05 | 18.88 | 2016-08-19 | 2016-09-05 | 2018-03-14 | 24 | 2019-03-26 | 2021-03-26 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
47 | Haryana | NR | DHVBN | Renovation and modernisation of distribution system of DHBVN, Haryana(077) | 2016-08-01 | 1381.77 | 2016-05-06 | 2016-05-31 | 364.27 | 5.1(d) | 75 | 2016-08-05 | 273.2 | 2016-08-19 | 2017-01-02 | 2017-11-24 | 18 | 2018-03-26 | 2019-09-26 |  |  |  |  | 1.378 | 1.632 | 6.0333 | 7.6653 | 9.0433 |  | 0 | 0 | 9.0433 |  |  | 0 | 9.0433
48 | Bihar | ER | BSPTCL | Renovation and Upgradation of the protection and control system of 12nos 132/33 Grid Sub Station. (73) | 2016-01-09 | 63.55 | 2016-06-14 | 2016-09-06 | 54.69 | 5.1 (c ) | 90 | 2016-11-24 | 49.22 | 2016-11-24 | 2017-01-02 | Scheme withdrawn | 24 |  | 1901-12-31 |  |  |  |  | 3.9266 | 0 |  | 0 | 3.9266 |  | 0 | 0 | 3.9266 |  |  | 0 | 3.9266
49 | Punjab | NR | PSTCL | Provision of Second DC Source at 220KV & 132KV Grid Sub Station of PSTCL. (70) | 2015-12-08 | 15.31 | 2016-08-01 | 2016-09-06 | 15.3 | 5.1 (c ) | 90 | 2016-11-24 | 13.78 | 2016-11-24 | 2017-01-02 | 2017-03-23 | 18 | 2018-03-22 | 2019-09-22 |  |  |  |  | 15.916 | 0.004 |  | 0.004 | 15.92 |  | 0 | 0 | 15.92 |  |  | 0 | 15.92
50 | SRPC | SR | SRPC | Study programme on the Integration of Renewables Enery Resources (RES) into the Grid. (78) | 2016-01-19 | 6.45 | 2016-08-01 | 2016-09-06 | 5.5 | 5.1 (e ) | 100 | 2016-11-24 | 5.5 | 2016-11-24 | 2017-01-02 | 2017-01-23 | 5 | 2017-08-23 | 2018-01-23 |  |  |  |  | 0.477 | 0.003 | 0.954 | 0.957 | 1.434 |  | 2.862 | 2.862 | 4.296 |  |  | 0 | 4.296
51 | SRPC | SR | SRPC | Procurement Web based management software and protection setting calculation tool. (79) | 2016-02-15 | 28 | 2016-08-01 | 2016-09-06 | 25.09 | 5.1 (e ) | 100 | 2016-11-24 | 25.09 | 2016-11-24 | 2017-01-02 | 2017-02-15 | 18 | 2017-09-20 | 2019-03-20 |  |  |  |  | 2.596 | 0.004 | 5.089 | 5.093 | 7.689 |  | 15.261 | 15.261 | 22.95 |  |  | 0 | 22.95
52 | Kerala | SR | KSEBL | Implementation of Automatic Demand Management Scheme (ADMS) at 322 Substations of KSEBL at 33kV level. (80) | 2016-02-29 | 6.035 | 2016-08-01 | 2016-09-06 | 5.3 | 5.1 (c ) | 90 | 2016-11-24 | 4.77 | 2016-11-24 | 2017-01-02 | 2017-03-21 | 30 | 2017-07-04 | 2020-01-04 |  |  |  |  | 0 | 1.2 | 1.174 | 2.374 | 2.374 |  | 3.782 | 3.782 | 6.156 | 0.124 |  | 0.124 | 6.28
53 | DVC | ER | DVC | Renovation and Upgradation of the protection and control system of Ramgarh Sub Station. (081) | 2016-04-04 | 39.87 | 2016-06-14 | 2016-09-06 | 28.85 | 5.1 (c ) | 90 | 2016-11-24 | 25.96 | 2016-11-24 | 2017-01-02 | 2017-04-11 | 24 | 2017-05-31 | 2019-05-31 |  |  |  |  | 0 | 2.91 |  | 2.91 | 2.91 |  | 0 | 0 | 2.91 |  |  | 0 | 2.91
54 | Tamil Nadu | SR | TANTRANSCO | Establishment of Technical and IT infrastructure for implementation of intra state ABT in Tamilnadu. (085) | 2016-05-23 | 168.1 | 2016-08-01 | 2016-09-06 | 13.31 | 5.1 (c ) | 90 | 2016-11-24 | 11.98 | 2016-11-24 | 2017-01-02 | 2017-11-24 | 24 | 2018-05-25 | 2020-05-25 |  |  |  |  | 100.175 | 0.005 | 155.057 | 155.062 | 255.237 |  | 45.293 | 45.293 | 300.53 |  |  | 0 | 300.53
55 | Gujarat | WR | GETCO | 220kV Super conducting fault current limiter (SCFCL) project (043) | 2015-02-24 | 48.13 | 2016-05-17 | 2016-09-06 | 32.37 | 5.1 (c ) | 90 | 2016-11-24 | 29.13 | 2016-11-24 | 2017-01-02 | 2018-02-23 | 24 | 2018-06-25 | 2020-06-25 |  |  |  |  | 16.67 | 0 |  | 0 | 16.67 |  | 30.854 | 30.854 | 47.524 |  |  | 0 | 47.524
56 | POWERGRID | Central | POWERGRID | Funding of BNC Agra HVDC (94) | 2016-06-21 | 5778 | 2016-07-05 | 2016-09-06 | 5778 | 4(3)(A) | 50 | 2016-11-24 | 2889 | 2016-11-24 | 2017-03-10 | 2017-05-23 | 54 | 2019-02-14 | 2023-08-14 |  |  |  |  | 14.05 | 0 | 16.335 | 16.335 | 30.385 |  | 71.957 | 71.957 | 102.342 |  |  | 0 | 102.342
57 | RECTPCL | Central | RECTPCL | 11kV Rural Feeder Monitoring. (111) | 2016-08-29 | 233.03 | 2016-09-26 | 2016-10-28 | 233.03 | 5.1( e) | 100 | 2016-11-24 | 233.03 | 2016-11-24 | 2017-03-10 | 2017-05-30 | 72 | 2017-10-27 | 2023-10-27 |  |  |  |  | 16.748 | 0.002 |  | 0.002 | 16.75 |  | 4.997 | 4.997 | 21.747 |  |  | 0 | 21.747
58 | Kerala | SR | KSEBL | Construction of Madakkathara – Areakode 400/220kV Multi-circuit Multi-voltage transmission Line (95km) & Construction of Kizhisseri-Nallalam 220/110kV Multi-Circuit Multi Voltage transmission line. (090) | 2016-05-31 | 371.03 | 2016-08-05 | 2016-10-28 | 371.03 | 5.1 (c ) | 90 | 2017-02-16 | 333.93 | 2017-04-10 | 2017-05-16 | 2017-08-23 | 24 | 2018-03-21 | 2020-03-21 |  |  |  |  | 0.654 | -0.004 |  | -0.004 | 0.65 |  | 2.801 | 2.801 | 3.451 |  |  | 0 | 3.451
59 | Kerala | SR | KSEBL | Up-rating Kakkayam - Nallalam 110kV line (45km) & Upgrading Nallalam- Chevayur-Westhill-Koyilandy110kV Single Circuit line in to Double Circuit line.(96) | 2016-05-31 | 89.03 | 2016-08-05 | 2016-10-28 | 89.03 | 5.1 (d) | 75 | 2017-05-05 | 66.85 | 2017-04-10 | 2017-05-16 | 2017-08-23 | 24 | 2018-03-21 | 2020-03-21 |  |  |  |  | 3.4425 | -0.0025 |  | -0.0025 | 3.44 |  | 1.01 | 1.01 | 4.45 |  |  | 0 | 4.45
60 | DVC | ER | DVC | Renovation and Modernization of control and protection system and replecement of equipment at Parulia, Durgapur, Kalyanewari, Giridhi Jamsedpur, Barjora, Burnpur, Dhanbad and Bundwan substation. (106) | 2016-08-08 | 191.31 | 2016-09-28 | 2016-10-28 | 156.11 | 5.1 (c ) | 90 | 2017-02-16 | 140.5 | 2017-04-10 | 2017-11-27 | 2017-06-21 | 24 | 2017-12-14 | 2019-12-14 |  |  |  |  | 0.139 | 1.111 | 0.1424 | 1.2534 | 1.3924 |  | 0 | 0 | 1.3924 |  |  | 0 | 1.3924
61 | Tamil Nadu | SR | TANTRANSCO | Renovation and Modernisation of Protection System of 400kV, 230kV & 110kV hydro Generating Stations. (084) | 2016-05-18 | 203.69 | 2016-07-05 | 2016-10-28 | 186.09 | 5.1 (c ) | 90 | 2017-02-16 | 167.48 | 2017-04-10 | 2017-05-16 | 2018-01-08 | 42 | 2018-03-23 | 2021-09-23 |  |  |  |  | 3.45 | 1.09 |  | 1.09 | 4.54 |  | 0 | 0 | 4.54 |  |  | 0 | 4.54
62 | Telangana | SR | TSGENCO | Renovation and Upgradation of protection system of substations (014) | 2014-09-01 | 32.86 | 2016-09-14 | 2016-10-28 | 7.27 | 5.1 (c ) | 90 | 2017-02-16 | 6.54 | 2017-04-10 | 2017-05-16 | 2017-07-11 | 12 | 2017-11-15 | 2018-11-15 | [7 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
63 | NERPC | NER | NERPC | Study programme on the Integration of Renewables Energy Resources (RES) into the Grid. (118) | 2016-09-30 | 8 | 2016-10-19 | 2016-10-28 | 6.5 | 5.1( e) | 100 | 2017-02-16 | 6.5 | 2017-04-10 | 2017-05-16 | 2017-06-01 | 3 | 2017-06-19 | 2017-09-19 |  |  |  |  | 0 | 9.3 |  | 9.3 | 9.3 |  | 0 | 0 | 9.3 |  |  | 0 | 9.3
64 | West Bengal | ER | WBPDCL | Implementation of Islanding scheme at Bandel Thermal Power Station. (097) | 2016-06-27 | 1.64 | 2016-09-28 | 2016-10-28 | 1.54 | 5.1( c) | 90 | 2017-05-05 | 1.39 | 2017-04-10 | 2017-05-16 | 2017-08-10 | 8 | 2017-12-14 | 2018-08-14 | [7 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
65 | Maharashtra | WR | MSETCL | Replacement of existing 0.15 ACSR wolf conductor of 132kV Balapur-Patur-Malegoan corridor by High Ampacity Conductor. (098) | 2016-07-01 | 51.25 | 2017-02-16 | 2017-03-10 | 46.15 | 5.1(d) | 75 | 2017-05-05 | 34.61 | 2017-04-10 | 2017-05-16 | 2017-12-19 | 6 | 2018-03-21 | 2018-09-21 | [7 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
66 | Maharashtra | WR | III: MSETCL; IV: Replacement of existing 0.2 ACSR wolf conductor of 132kV Khapri-Besa (Nagpur Ring Main Line) High Ampacity Conductor. (099); V: 2016-07-01; VII: 2017-02-16; VIII: 2017-03-10 | [10 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
67 | Maharashtra | WR | MSETCL | Installation of Shunt Bus Reactors at 400KV Solapur, 400 KV Kolhapur and 400kV Karad substations. (100) | 2016-07-18 | 129.33 | 2017-02-16 | 2017-03-10 | 103.38 | 5.1(b) | 90 | 2017-05-05 | 93.04 | 2017-04-10 | 2017-12-22 | 2018-04-25 | 12 | 2018-06-25 | 2019-06-25 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
68 | Maharashtra | WR | III: MSETCL; IV: Installation of Shunt Bus Reactors at 400KV Akola, 400 KV Bhusawal-II and 400kV Nanded substations. (101); V: 2016-07-18; VII: 2017-02-16; VIII: 2017-03-10; IX: 0; X: 5.1(b) | [7 empty] | 0.937 | 0.003 |  | 0.003 | 0.94 |  | 0 | 0 | 0.94 |  |  | 0 | 0.94
69 | Maharashtra | WR | III: MSETCL; IV: Installation of Shunt Bus Reactors at 400KV Koradi, 400 KV Khaparkheda and 400kV Chandrapur-II substations. (102); V: 2016-07-18; VII: 2017-02-16; VIII: 2017-03-10; IX: 0; X: 5.1(b) | [7 empty] | 4.748 |  | 9.497 | 9.497 | 14.245 |  | 28.48 | 28.48 | 42.725 |  |  | 0 | 42.725
70 | Maharashtra | WR | III: MSETCL; IV: Installation of Shunt Bus Reactors at 400KV Lonikand-II, 400 KV Chakan and 400kV Kudus substations. (103); V: 2016-07-18; VII: 2017-02-16; VIII: 2017-03-10; IX: 0; X: 5.1(b) | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0.45 | 0.45 | 0.45 |  |  | 0 | 0.45
71 | Maharashtra | WR | MSETCL | 75 Nos. RTUs for 132 kv Substations in Maharashtra (104) | 2016-07-18 | 32.04 | 2017-02-16 | 2017-03-10 | 25.65 | 5.1(c) | 30 | 2017-05-05 | 7.7 | 2017-04-10 | 2017-05-16 |  | 18 | [6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
72 | Maharashtra | WR | MSETCL | 30 Nos. of Data Concentrators in MSETCL networks. (114) | 2016-08-19 | 13.12 | 2017-02-16 | 2017-03-10 | 10.41 | 5.1(c) | 90 | 2017-05-05 | 9.37 | 2017-04-10 | 2017-05-16 | 2017-10-10 | 12 | 2017-12-14 | 2018-12-14 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 2.555 | 2.555 | 2.555 |  |  | 0 | 2.555
73 | Uttar Pradesh | NR | UPPTCL | Replacement of existing ACSR conductor by HTLS conductor for reliving congestion. (89) | 2016-05-23 | 63.31 | 2017-02-16 | 2017-03-10 | 63.31 | 5.1(d) | 75 | 2017-05-05 | 47.48 | 2017-04-10 | 2017-05-16 | 2017-07-27 | 18 | 2017-09-20 | 2019-03-20 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
74 | Chhattisgarh | WR | CSPTCL | Implementation of Automatic Demand Management Scheme (ADMS) in the Chhattisfgarh State. (112) | 2016-08-29 | 5.68 | 2017-02-16 | 2017-03-10 | 5.03 | 5.1(c) | 90 | 2017-05-05 | 4.53 | 2017-04-10 | 2017-05-16 | 2019-09-03 | 24 | 2019-12-31 | 2021-12-31 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
75 | Gujarat | WR | PGVCL | Installation of capacitor banks for reactive power compensation system on 11kV feeders. (121) | 2016-11-10 | 82.85 | 2017-01-19 | 2017-04-17 | 63.32 | 5.1 (b ) | 90 | 2017-05-15 | 56.99 | 2017-05-01 | 2017-05-22 | 2017-08-01 | 36 | [6 empty] | 1.415 | 0.005 | 2.469 | 2.474 | 3.889 |  | 7.401 | 7.401 | 11.29 |  |  | 0 | 11.29
76 | Gujarat | WR | MGVCL | Installation of capacitor banks for reactive power compensation system on 11kV feeders. (50) | 2015-03-05 | 37.15 | 8-Jan-16 | 2017-04-17 | 28.39 | 5.1 (b ) | 90 | 2017-05-15 | 25.55 | 2017-05-01 | 2017-05-22 | 2018-03-26 | 30 | 2019-05-13 | 2021-11-13 |  |  |  |  | 2.932 | -0.002 |  | -0.002 | 2.93 |  | 0 | 0 | 2.93 |  |  | 0 | 2.93
77 | Gujarat | WR | UGVCL | Installation of capacitor banks for reactive power compensation system on 11kV feeders. (53) | 2015-03-09 | 37.51 | 8-Jan-16 | 2017-04-17 | 15.63 | 5.1 (b ) | 90 | 2017-05-15 | 14.07 | 2017-05-01 | 2017-05-22 | 2018-01-10 | 36 | [6 empty] | 0 | 6.6 | 5.09 | 11.69 | 11.69 |  | 21.38 | 21.38 | 33.07 |  |  | 0 | 33.07
78 | Gujarat | WR | DGVCL | Installation of capacitor banks for reactive power compensation system on 11kV feeders. (71) | 2015-12-10 | 21.73 | 2016-01-08 | 2017-04-17 | 15.77 | 5.1 (b ) | 90 | 2017-05-15 | 14.19 | 2017-05-01 | 2017-05-22 | 2018-01-29 | 30 | [6 empty] | 0 | 21.06 | 42.08 | 63.14 | 63.14 |  | 0 | 0 | 63.14 |  |  | 0 | 63.14
79 | Maharashtra | WR | MSETCL | Installation of Capacitor Banks at HV & EHV level at various EHV subatations under Nashik & Pune zones in MSETCL. (086) | 2016-05-20 | 19.49 | 2017-01-19 | 2017-04-17 | 15.72 | 5.1 (b ) | 90 | 2017-05-15 | 14.15 | 2017-05-01 | 2017-05-22 | 2017-10-10 | 12 | 2018-01-03 | 2019-01-03 |  |  |  |  | 1.337 | 0.003 |  | 0.003 | 1.34 |  | 0 | 0 | 1.34 |  |  | 0 | 1.34
80 | Maharashtra | WR | MSETCL | Implementation of ADMS scheme on 33/11kV feeders in Maharashtra. (113) | 2016-08-19 | 43.73 | 2017-03-31 | 2017-04-17 | 32.58 | 5.1(c) | 90 | 2017-05-15 | 29.32 | 2017-05-01 | 2017-05-22 | 2017-10-10 | 18 | 2018-01-03 | 2019-07-03 |  |  |  |  | 0 | 2.24 |  | 2.24 | 2.24 |  | 1.83 | 1.83 | 4.07 |  |  | 0 | 4.07
81 | West Bengal | ER | WBSETCL | Installation of switchable reactor & shunt capacitor for voltage improvement. (88) | 2016-02-03 | 48.45 | 2016-01-08 | 2017-04-17 | 48.19 | 5.1 (b ) | 90 | 2017-05-15 | 43.37 | 2017-05-01 | 2017-05-22 | 2017-08-10 | 19 | 2018-06-22 | 2020-01-22 |  |  |  |  | 1.186 | 0.004 |  | 0.004 | 1.19 |  | 0 | 0 | 1.19 |  |  | 0 | 1.19
82 | West Bengal | ER | WBSETCL | Renovation & Modernisation of Transmission System for relieving congestion in intra state transmission system by capacity enhancement of existing network. (087) | 2016-02-03 | 72.65 | 2017-03-31 | 2017-04-17 | 93.51 | 5.1(d) | 75 | 2017-05-15 | 70.13 | 2017-05-01 | 2017-05-22 | 2017-08-10 | 25 | 2018-06-25 | 2020-07-25 |  |  |  |  | 0 | 56.59 | 28.489 | 85.079 | 85.079 |  | 171.31 | 171.31 | 256.389 |  |  | 0 | 256.389
83 | Manipur | NER | Manipur SLDC | 33kV system Integration with SLDC system in manipur. (093) | 2017-05-16 | 77.01 | 2017-03-31 | 2017-04-17 | 13.37 | 5.1(c) | 100 | 2017-05-15 | 13.37 | 2017-05-01 | 2017-05-22 | 2017-11-09 | 18 | 2018-03-27 | 2019-09-27 |  |  |  |  | 0 | 0 | 17.739 | 17.739 | 17.739 |  | 40.894 | 40.894 | 58.633 |  |  | 0 | 58.633
84 | Odisha | ER | OHPCL | Renovation and Upgradation of protection and control system of OHPC. (109) | 2016-08-23 | 38.93 | 2017-03-31 | 2017-04-17 | 24.83 | 5.1(c) | 90 | 2017-05-15 | 22.35 | 2017-05-01 | 2017-05-22 | 2017-09-19 | 24 | 2018-05-25 | 2020-05-25 |  |  |  |  | 0.671 | -0.001 |  | -0.001 | 0.67 |  | 0 | 0 | 0.67 |  |  | 0 | 0.67
85 | Rajasthan | NR | RRVPNL | "Smart Transmission Operation Management System (STOMS) " in Rajasthan Power System. (110) | 2016-08-29 | 29.95 | 2017-03-31 | 2017-04-17 | 13.18 | 5.1(c) | 90 | 2017-05-15 | 11.86 | 2017-05-01 | 2017-05-19 | 2017-10-10 | 12 | 2018-03-27 | 2019-03-27 |  |  |  |  | 0 | 0 | 39.83 | 39.83 | 39.83 |  | 76.746 | 76.746 | 116.576 |  |  | 0 | 116.576
86 | Rajasthan | NR | RRVPNL | Communication Backbone "Smart Transmission Network & Asset Management Systeem" Part-B (136) | 2017-02-20 | 586.87 | 2017-03-31 | 2017-04-17 | 569.77 | 5.1(c) | 50 | 2017-05-15 | 284.89 | 2017-05-01 | 2017-05-22 | 2017-10-10 | 18 | 2018-06-22 | 2019-12-22 |  |  |  |  | 0 | 2.33 | 1.96 | 4.29 | 4.29 |  | 7.09 | 7.09 | 11.38 |  |  | 0 | 11.38
87 | Telangana | SR | TSTRANSCO | Relieving of Transmission Congestion of existing Overloaded 220kV Lines in Hydrabad city. (119) | 2016-10-31 | 107.4 | 2017-03-31 | 2017-04-17 | 78.84 | 5.1(d) | 75 | 2017-05-15 | 59.13 | 2017-05-01 | 2017-05-22 | 2017-06-27 | 18 | 2019-03-28 | 2020-09-28 |  |  |  |  | 0 | 0 | 7.892 | 7.892 | 7.892 |  | 0.088 | 0.088 | 7.98 |  |  | 0 | 7.98
88 | Madhya Pradesh | WR | MPPGCL | Installation of : 50 MVAR Line Reactor at 400kV substation at Sarni, Dist. Betul. (123) | 2016-12-14 | 7.45 | 2017-03-31 | 2017-04-17 | 7.45 | 5.1(b) | 60 | 2017-05-15 | 6.71 | 2017-05-01 | 2017-05-22 | 2018-01-19 | 12 | 2018-03-21 | 2019-03-21 |  |  |  |  | 0 | 0 | 9.26 | 9.26 | 9.26 |  | 17.592 | 17.592 | 26.852 |  |  | 0 | 26.852
89 | Andhra Pradesh | SR | APTRANSCO | Project on providing of Reliable communication and Data acquisition system upto 132kV SS. (127) | 2017-01-30 | 383.22 | 2017-03-31 | 2017-04-17 | 284.96 | 5.1(c) | 50 | 2017-05-15 | 142.48 | 2017-05-01 | 2017-05-23 | 2017-08-24 | 24 | 2019-03-28 | 2021-03-28 |  |  |  |  | 0 | 2.02 | 0.648 | 2.668 | 2.668 |  | 1.97 | 1.97 | 4.638 | 5.202 |  | 5.202 | 9.84
90 | POWERGRID | SR | POWERGRID | Installation of STATCOM in SR region at Hydrabad, Udumalpet & Trichy substations of Powergrid. (75) | 2016-01-07 | 472.55 | 2016-05-05 | 2017-04-17 | 472.55 | 5.1(b) | 80 | 2017-05-15 | 378.04 | 2017-05-01 | 2017-05-22 | 2017-10-10 | 30 | 2017-11-15 | 2020-05-15 |  |  |  |  | 0 | 0 | 2.561 | 2.561 | 2.561 |  | 5.119 | 5.119 | 7.68 |  |  | 0 | 7.68
91 | BBMB | NR | BBMB(038) | Renovation and Upgradation of protection system of substations. (038) | 2015-01-06 | 28.48 | 2016-01-08 | 2016-03-08 | 25.86 | 5.1 (c ) | 90 | 2017-05-15 | 23.27 | 2017-08-25 | 2017-11-15 | 2018-02-19 | 22 | 2018-06-25 | 2020-04-25 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 1.873 | 1.873 | 1.873 |  |  | 0 | 1.873
92 | Telangana | SR | TSTRANSCO | Implementation of OPGW based reliable communication at 132 kv and above substations. (137) | 2017-03-14 | 185.23 | 2017-06-21 | 2017-07-04 | 159.63 | 5.1(c ) | 50 | 2017-10-04 | 79.82 | 2017-08-25 | 2017-11-15 | 2018-03-21 | 24 | 2019-03-28 | 2021-03-28 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 7.376 | 7.376 | 7.376 | 9.402 |  | 9.402 | 16.778
93 | Rajasthan | NR | RRVPNL | Real Time Data Acquisition System for Monitoring & Control of Transmission Grid under STNAMS (PART A-1) (153) | 2017-04-26 | 191.72 | 2017-06-21 | 2017-07-04 | 185.19 | 5.1(c ) | 50 | 2017-10-04 | 92.6 | 2017-08-25 | 2017-11-15 | 2018-02-23 | 24 | 2019-03-26 | 2021-03-26 |  |  |  |  | 0 | 25.395 |  | 25.395 | 25.395 |  | 8.552 | 8.552 | 33.947 |  |  | 0 | 33.947
94 | Kerala | SR | KSEBL | Renovation & Up gradation of Various 220 kv switchyard Equipment. (126) | 2017-01-25 | 61.37 | 2017-06-21 | 2017-07-04 | 22.42 | 5.1(c ) | 90 | 2017-10-04 | 20.18 | 2017-08-25 | 2017-11-15 | 2018-02-15 | 24 | 2018-06-25 | 2020-06-25 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 15.55 | 15.55 | 15.55 | 10.8 | 10.38 | 21.18 | 36.73
95 | Odisha | ER | OPTCL | Implementation of OPGW based reliable communication at 132 kv and above substations. (128) | 2017-02-09 | 80.62 | 2017-06-21 | 2017-07-04 | 51.22 | 5.1(c ) | 50 | 2017-10-04 | 25.61 | 2017-08-25 | 2017-11-15 | 2018-01-03 | 36 | 2019-03-29 | 2022-03-29 |  |  |  |  | 0 | 0.41 |  | 0.41 | 0.41 |  | 0 | 0 | 0.41 |  |  | 0 | 0.41
96 | Uttrakhand | NR | PTCUL | Implementation of OPGW based reliable communication at 132 kv and above substations. (129) | 2017-02-10 | 43.39 | 2017-06-21 | 2017-07-04 | 37.46 | 5.1(c ) | 50 | 2017-10-04 | 18.73 | 2017-08-25 | 2017-11-15 | 2018-11-28 | 36 | 2019-05-15 | 2022-05-15 |  |  |  |  | 0 | 0 | 39.119 | 39.119 | 39.119 |  | 75.56 | 75.56 | 114.679 |  |  | 0 | 114.679
97 | Kerala | SR | KSEBL | Implementation of OPGW based reliable communication at 132 kv and above substations. (141) | 2017-03-16 | 212.45 | 2017-06-21 | 2017-07-04 | 147.52 | 5.1(c ) | 50 | 2017-10-04 | 73.76 | 2017-08-25 | 2017-11-15 | 2019-04-16 | 36 | 2019-05-15 | 2022-05-15 |  |  |  |  | 0 | 0 | 1.611 | 1.611 | 1.611 |  | 3 | 3 | 4.611 |  |  | 0 | 4.611
98 | Gujarat | WR | GETCO | Implementation of OPGW based reliable communication at 132 kv and above substations. (143) | 2017-03-27 | 576.64 | 2017-06-21 | 2017-07-04 | 507.89 | 5.1(c ) | 50 | 2017-10-04 | 253.95 | 2017-08-25 | 2017-11-15 | 2018-02-12 | 36 | 2018-05-25 | 2021-05-25 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0.18 | 0.18 | 0.18 | 0.36187 |  | 0.36187 | 0.54187
99 | Tamil Nadu | SR | TANTRANSCO | Implementation of OPGW based reliable communication at 132 kv and above substations. (151) | 2017-04-24 | 374.42 | 2017-06-21 | 2017-07-04 | 310.96 | 5.1(c ) | 50 | 2017-10-04 | 155.48 | 2017-08-25 | 2017-11-15 | 2019-06-03 | 24 | 2019-12-20 | 2021-12-20 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
100 | Manipur | NER | MSPCL | Implementation of OPGW based reliable communication at 132 kv and above substations. (152) | 2017-04-26 | 11.36 | 2017-06-21 | 2017-07-04 | 8.15 | 5.1(c ) | 50 | 2017-10-04 | 4.08 | 2017-08-25 | 2017-11-15 | 2018-01-29 | 18 | 2018-05-25 | 2019-11-25 |  |  |  |  | 0 | 0 | 4.516 | 4.516 | 4.516 |  | 7.502 | 7.502 | 12.018 |  |  | 0 | 12.018
101 | Jharkhand | ER | JUSNL | Renovation and Upgradation of protection system of substations. (161) | 2017-06-05 | 186.31 | 2017-06-21 | 2017-07-04 | 153.48 | 5.1(c ) | 90 | 2017-10-04 | 138.13 | 2017-08-25 | 2017-11-15 | 2018-07-03 | 16 | 2019-03-28 | 2020-07-28 |  |  |  |  | 0 | 0 | 12.679 | 12.679 | 12.679 |  | 0 | 0 | 12.679 |  |  | 0 | 12.679
102 | ERPC | ER | ERPC | Study Programme on power trading at NORD POOL Academy for Power System Engineers of Eastern Region. (122) | 2016-12-05 | 6.2 | 2017-06-21 | 2017-07-04 | 5.46 | 5.1(e ) | 100 | 2018-06-14 | 5.46 | 2018-05-02 | 2018-07-27 | 2018-09-21 | 60 | 2019-03-27 | 2024-03-27 |  |  |  |  | 0 | 0 | 1.933 | 1.933 | 1.933 |  | 0 | 0 | 1.933 |  |  | 0 | 1.933
103 | ERPC | ER | ERPC | Traning Program for Power system Engineers of various constituents of Eastern Region. (117) | 2016-09-29 | 1.01 | 2017-06-21 | 2017-07-04 | 0.61 | 5.1(e ) | 100 | 2018-06-14 | 0.61 | 2018-05-02 | 2018-07-27 | 2018-09-21 | 60 | 2019-04-11 | 2024-04-11 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 3.305 | 3.305 | 3.305 |  |  | 0 | 3.305
104 | Chhattisgarh | WR | CSPTCL | Reliable Communication and data Acquisition System upto 132kV Substation in Chhattisgarh. (125) | 2017-01-25 | 145.91 | 2017-09-29 | 2018-02-05 | 145.91 | 5.1(c ) | 50 | 2018-06-14 | 72.96 | 2018-05-02 | 2018-07-27 | 2020-11-18 | 18 | [6 empty] | 0 | 0 |  | 0 | 0 |  | 20.91 | 20.91 | 20.91 |  |  | 0 | 20.91
105 | West Bengal | ER | WBPDCL | Renovation and Modernization of switchyard and related protection system of different power stations (BTPS, BKTPS and KTPS) of WBPDCL (155) | 2017-04-26 | 110.5 | 2017-09-29 | 2018-02-05 | 50.18 | 5.1(c ) | 90 | 2018-06-14 | 45.16 | 2018-05-02 | 2018-07-27 | 2018-12-20 | 12 | 2019-03-27 | 2020-03-27 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 2.479 | 2.479 | 2.479 |  |  | 0 | 2.479
106 | Karnataka | SR | KPTCL | Reliable Communication and data Acquisition System upto 132kV Substation in Karnataka. (149) | 2017-04-06 | 292.88 | 2017-09-29 | 2018-02-05 | 253.57 | 5.1(c ) | 50 | 2018-06-14 | 126.79 | 2018-05-02 | 2018-07-27 | 2019-01-25 | 36 | 2019-04-01 | 2022-04-01 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 20.69 | 20.69 | 20.69 |  |  | 0 | 20.69
107 | Andhra Pradesh | SR | APTRANSCO | Project on Scheduling, accounting, Meeting and Settlement of Transmission in Electricity (SAMAST) IN Transmission Corporation of Andhra Pradesh (147) | 2017-04-06 | 52.72 | 2017-11-15 | 2018-02-05 | 21.48 | 5.1(c ) | 90 | 2018-06-14 | 19.33 | 2018-05-02 | 2018-07-27 | 2018-11-28 | 24 | 2019-03-27 | 2021-03-27 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 1.307 | 1.307 | 1.307 |  |  | 0 | 1.307
108 | Punjab | NR | PSTCL | Reliable Communication and Data Acquisition System upto 132kV Substation in Punjab. (138) | 2017-03-14 | 66.8 | 2017-09-29 | 2018-02-05 | 66.1 | 5.1(c ) | 50 | 2018-06-14 | 33.05 | 2018-05-02 | 2018-07-27 | 2018-11-14 | 36 | 2019-06-25 | 2022-06-25 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
109 | Himachal Pradesh | NR | HPSEBL | Strengthening of Transmission System incidentals to Inter-State- Transmission System in the State of HP (134) | 2017-02-23 | 106.17 | 2017-11-15 | 2018-02-05 | 24.38 | 5.1(d) | 100 | 2018-06-14 | 24.38 | 2018-05-02 | 2018-07-27 | 2019-04-16 | 18 | 2019-08-08 | 2021-02-08 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 2.723 | 2.723 | 2.723 |  |  | 0 | 2.723
110 | Himachal Pradesh | NR | HPSEBL | Reliable Communication and data Acquisition System upto 132kV Substation in Himachal Pradesh (135) | 2017-02-23 | 10.77 | 2017-09-29 | 2018-02-05 | 18.64 | 5.1(c ) | 50 | 2018-06-14 | 9.32 | 2018-05-02 | 2018-07-27 | 2019-04-16 | 18 | 2019-08-08 | 2021-02-08 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
111 | Madhya Pradesh | WR | MPPTCL | Reliable Communication and data Acquisition System upto 132kV Substation in Madhya Pradesh. (144) | 2017-04-06 | 506.51 | 2018-02-26 | 2018-03-22 | 413.79 | 5.1(c ) | 50 | 2018-07-20 | 206.89 | 2018-05-02 | 2018-07-27 | 2019-03-16 | 36 | 2019-12-23 | 2022-12-23 |  |  |  |  | 0 | 0 | 5.387 | 5.387 | 5.387 |  | 10.763 | 10.763 | 16.15 |  |  | 0 | 16.15
112 | Madhya Pradesh | WR | MPPGCL | Installation of 125MVAR Bus Reactor at 400kV Switchyard Sanjay Gandhi TPS, at Substations at Birsinghpur under PSDF. (167) | 2017-07-09 | 22.01 | 2018-02-26 | 2018-03-22 | 14.52 | 5.1(b) | 90 | 2018-07-20 | 13.07 | 2018-05-02 | 2018-07-27 | 2018-10-03 | 12 | 2019-05-10 | 2020-05-10 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
113 | Madhya Pradesh | WR | III: MPPGCL; IV: Installation of 125MVAR Bus Reactor at 400kV Switchyard at Shree Singaji TTP Stage-II, Dist: Khandwa. (174); V: 2017-08-09; VII: 2018-02-26; VIII: 2018-03-22 | [7 empty] | 21.78 | 0 | 29.1 | 29.1 | 50.88 |  | 0 | 0 | 50.88 |  |  | 0 | 50.88
114 | Odisha | ER | OPTCL | Installation of 125 MVAR Bus Reactor along with construction of associated by each at 400kV Grid S/S of Mendhasal, Meramundali & New Duburi for VAR control & stabilisation of system voltage. (179) | 2017-08-28 | 31.94 | 2017-11-16 | 2018-03-22 | 30.26 | 5.1(b) | 90 | 2018-07-20 | 27.23 | 2018-05-02 | 2018-07-27 | 2018-09-21 | 18 | 2019-04-01 | 2020-10-01 | [7 empty] | 0 | 0 |  | 0.35 | 0.35 | 0.35 | 0.896 |  | 0.896 | 1.246
115 | Puducherry | SR | DoP, Puducherry | Project on providing of Reliable Communication & Data Acquisition system upto 132kV SS. (180) | 2017-08-28 | 15.01 | 2018-02-26 | 2018-03-22 | 7.37 | 5.1(c ) | 50 | 2018-07-20 | 3.69 | 2018-05-02 | 2018-07-27 | 2019-10-03 | 24 | 2020-09-15 | 2022-09-15 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 0.309 |  | 0.309 | 0.309
116 | NERPC | NER | NERPC | Protection Data base management System. The project will be implemented in following States: Arunachal Pradesh, Assam, Manipur, Meghalaya, Mizoram, Nagaland & Tripura. (201) | 2018-01-08 | 26.74 | 2018-02-26 | 2018-03-22 | 18 | 5.1(e ) | 100 | 2018-07-20 | 18 | 2018-05-02 | 2018-07-27 | 2018-08-20 | 18 | 2019-03-26 | 2020-09-26 | [7 empty] | 0 | 0 |  | 0.33 | 0.33 | 0.33 |  |  | 0 | 0.33
117 | NRPC | NR | NRPC | Creation and Maintenance of Web based Protection Database Management and PC based Protection Setting Calculation Tool for Northern Region Power System Network. (203) | 2018-01-12 | 35 | 2018-02-26 | 2018-03-22 | 28 | 5.1(e ) | 100 | 2018-07-20 | 28 | 2018-05-02 | 2018-07-27 | Scheme withdrawn | 18 | [9 empty] | 0 | 0 |  |  | 0 | 0 | 0.403 |  | 0.403 | 0.403
118 | Manipur | NER | MSPCL | Implementation of Automatic Demand Management Scheme (ADMS) Pilot Projects at Three Power Substation in Manipur(140) | 2017-03-16 | 6.55 | 2018-05-31 | 2018-06-25 | 2.24 | 5.1 (c) | 100 | 2018-12-06 | 2.24 | 2019-01-07 | 2019-05-24 | 2019-10-21 | 9 | 2020-01-01 | 2020-10-01 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
119 | Arunachal Pradesh | NER | DoP, Arunachal Pradesh | Implementation of Automatic Demand Management System (ADMS) to integrate33/11kV System with Arunachal Pradesh SLDC. (146) | 2017-04-06 | 4.99 | 2018-05-31 | 2018-06-25 | 1.97 | 5.1 (c) | 100 | 2018-12-06 | 1.97 | 2019-01-07 | 2019-05-24 | 2020-03-11 | 9 | 2020-06-11 | 2021-03-11 | [7 empty] | 0 | 0 |  | 0.983 | 0.983 | 0.983 |  |  | 0 | 0.983
120 | Nagaland | NER | DOP, Nagaland | 33/11kV System integration with SLDC System (ADMS) in Nagaland . (145) | 2017-04-06 | 5.09 | 2018-05-31 | 2018-06-25 | 2.12 | 5.1 (c) | 100 | 2018-12-06 | 2.12 | 2019-01-07 | 2019-05-24 | 2019-10-03 | 9 | 2019-01-21 | 2019-10-21 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
121 | Mizoram | NER | DOP, Mizoram | 33/11kV System integration with SLDC System Automatic Demand Management Scheme (ADMS) in Mizoram. (148) | 2017-04-06 | 5.4 | 2018-05-31 | 2018-06-25 | 1.97 | 5.1 (c) | 100 | 2018-12-06 | 1.97 | 2019-01-07 | 2019-05-24 | 2019-12-31 | 6 | 2020-07-16 | 2021-01-16 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
122 | Assam | NER | APDCL | 33/11kV System Integration with SLDC System (ADMS) in Assam. (156) | 2017-05-08 | 5 | 2018-05-31 | 2018-06-25 | 3.26 | 5.1 (c) | 100 | 2018-12-06 | 3.26 | 2019-01-07 | 2019-05-24 | 2020-05-23 | 6 | 2020-08-11 | 2021-02-11 | [7 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
123 | Meghalaya | NER | MePDCL | 33/11kV System integration with SLDC system in (ADMS) Meghalaya. (166) | 2017-07-10 | 2.07 | 2018-05-31 | 2018-06-25 | 2.07 | 5.1 (c) | 100 | 2018-12-06 | 2.07 | 2019-01-07 | 2019-05-24 | 2019-08-21 | 6 | 2019-12-31 | 2020-06-30 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 3 |  | 3 | 3
124 | Tripura | NER | TSECL | Implementation of Automatic Demand Management System (ADMS) in SLDC, Tripura. (226) | 2018-05-25 | 2.32 | 2018-05-31 | 2018-06-25 | 2.32 | 5.1 (c) | 100 | 2018-12-06 | 2.32 | 2019-01-07 | 2019-05-24 | 2020-05-15 | 9 | 2020-10-07 | 2021-07-07 | [7 empty] | 0 | 0 |  | 0.95 | 0.95 | 0.95 | 1.841 |  | 1.841 | 2.791
125 | Odisha | ER | OPTCL | Implementation of Automatic Demand Management System (ADMS) in SLDC, Odisha. (196) | 2017-12-22 | 3.26 | 2018-05-31 | 2018-06-25 | 3.26 | 5.1 (c) | 90 | 2018-12-06 | 2.93 | 2019-01-07 | 2019-05-24 | 2019-12-18 | 10 | 2020-02-19 | 2020-12-19 | [7 empty] | 0 | 0 |  | 0 | 0 | 0 |  | 15.384 | 15.384 | 15.384
126 | Jharkhand | ER | JUSNL | Reliable Communication & Data Acquistion System upto 132kV Substaions ER .(177) | 2017-08-23 | 102.31 | 2018-05-31 | 2018-06-25 | 44.72 | 5.1 (c) | 50 | 2018-12-06 | 22.36 | 2019-01-07 | 2019-05-24 | 2020-03-16 | 24 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
127 | Sikkim | ER | ENPD Sikkim | Drawing of optical ground wire (OPGW) cables on existing 132kV & 66kV transmission lines and integration of leftover substations with State Load Despatch Centre, Sikkim. (173) | 2017-08-09 | 25.36 | 2018-05-31 | 2018-06-25 | 20 | 5.1 (c) | 50 | 2018-12-06 | 10 | 2019-01-07 | 2019-05-24 | 2019-12-04 | 18 | 2020-06-04 | 2021-12-04 | [7 empty] | 0 | 0 |  | 1.582 | 1.582 | 1.582 |  |  | 0 | 1.582
128 | Meghalaya | NER | MePTCL | Installation of Numerical line differential relays in the 132kV transmission lines. (Short Lines). (186) | 2017-10-30 | 4.51 | 2018-10-30 | 2018-11-15 | 3.27 | 5.1 (b) | 100 | 2019-03-13 | 3.27 | 2019-01-07 | 2019-05-24 | 2019-08-21 | 18 | 2019-12-18 | 2021-06-18 | [7 empty] | 0 | 0 |  | 3.05 | 3.05 | 3.05 |  |  | 0 | 3.05
129 | West Bengal | ER | WBSETCL | Imstalltion of Bus Reactors at different 400kV Substation within the state of West Bengal for reactive power management of the Grid. (210) | 2018-03-12 | 79.71 | 2018-10-30 | 2018-11-15 | 79.71 | 5.1 (b) | 90 | 2019-03-13 | 71.74 | 2019-01-07 | 2019-05-24 | 2019-06-24 | 19 | 2020-02-19 | 2021-09-19 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
130 | Haryana | NR | HVPN | Reliable Communiacation System for 132 kV & above network in Haryana. (224) | 2018-05-22 | 219.78 | 2018-10-30 | 2018-11-15 | 175.51 | 5.1 (c) | 50 | 2019-03-13 | 87.75 | 2019-01-07 | 2019-05-24 | 2019-08-16 | 36 | [9 empty] | 0 | 0 |  | 13.26 | 13.26 | 13.26 |  |  | 0 | 13.26
131 | Rajasthan | NR | RRVPNL | Installation of 1x25 MVAR, 220kV Bus Reactor each at 400kV GSS Akal, 220kV GSS Suratgarh & 220kV GSS Bikaner. (223) | 2018-05-22 | 22.77 | 2018-10-30 | 2018-11-15 | 17.58 | 5.1 (b) | 90 | 2019-03-13 | 15.82 | 2019-01-07 | 2019-05-24 | 2019-10-16 | 18 | 2020-03-16 | 2021-09-16 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 4.439 |  | 4.439 | 4.439
132 | Punjab | NR | PSTCL | Provision of Bus Reactors at 400kV Grid Substations of PSTCL. (158) | 2017-05-29 | 52 | 2018-10-30 | 2018-11-15 | 33.92 | 5.1 (b) | 90 | 2019-03-13 | 30.53 | 2019-01-07 | 2019-05-24 | 2019-09-02 | 18 | 2019-12-16 | 2021-06-16 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 2.463 |  | 2.463 | 2.463
133 | Maharashtra | WR | MSETCL | Implementation & Supply of Numerical Line differential as Main-I Protection with inbuilt distance Relays towards Retrofit of existing protection schemes on 400kV lines at various 400kV substations in MSETCL. (238) | 2018-07-03 | 4.072 | 2018-10-30 | 2018-11-15 | 4.07 | 5.1 (b) | 90 | 2019-03-13 | 3.66 | 2019-01-07 | 2019-05-24 |  | 14 | [9 empty] | 0 | 0 |  |  | 0 | 0 | 2.689 |  | 2.689 | 2.689
134 | Andhra Pradesh | SR | APTRANSCO | Project on commissioning of 125MVAR Bus Reactors on 400kV SS Sattenapalli and 400kV SS Chittoor in Transmission Corporation of Andhra Pradesh. (Part-1) (239) | 2018-07-16 | 18.7797 | 2018-10-30 | 2018-11-15 | 16.37 | 5.1 (b) | 90 | 2019-03-13 | 14.73 | 2019-01-07 | 2019-05-24 | 2019-08-23 | 12 | 2019-10-23 | 2020-10-23 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 2.335 |  | 2.335 | 2.335
135 | Tamil Nadu | SR | TAN TRANSCO | Supply, Erection, Testing & Commissioning of 2 Nos. of 400kV, 80 MVAR Bus reactor with associated equipments for 400/230-110 kV AIS SS at Kamudhi under total turnkey cintract cintract in Madurai Region of Tamilnadu. (188) | 2017-10-30 | 17.27 | 2018-10-30 | 2018-11-15 | 16.44 | 5.1 (b) | 90 | 2019-03-13 | 14.8 | 2019-01-07 | 2019-05-24 | 2020-01-22 | 6 | 2020-06-23 | 2020-12-23 | [7 empty] | 0 | 0 |  | 3.66 | 3.66 | 3.66 |  |  | 0 | 3.66
136 | Tamil Nadu | SR | TAN TRANSCO | Supply, Erection, Testing & Commissioning of 1 Nos. of 400kV, 125 MVAR Bus reactor with associated equipments for 400/230-110 kV SS at Kayathar under total turnkey contract in Tiruneveli Region of Tamilnadu. (193) | 2017-12-06 | 9.58 | 2018-10-30 | 2018-11-15 | 9.12 | 5.1 (b) | 90 | 2019-03-13 | 8.21 | 2019-01-07 | 2019-05-24 | 2020-01-22 | 8 | 2020-06-23 | 2021-02-23 | [7 empty] | 0 | 0 |  | 3.12 | 3.12 | 3.12 |  |  | 0 | 3.12
137 | Tamil Nadu | SR | TAN TRANSCO | Supply, Erection, Testing & Commissioning of 1 Nos. of 400kV, 125 MVAR Bus reactor with associated equipments for 400kV SS at Alamathy under total turnkey contract in Chennai North Region of Tamilnadu. (202) | 2018-01-09 | 11.55 | 2018-10-30 | 2018-11-15 | 9.96 | 5.1 (b) | 90 | 2019-03-13 | 8.96 | 2019-01-07 | 2019-05-24 | 2020-01-22 | 8 | 2020-06-23 | 2021-02-23 |  |  |  |  | 173.99 | 0 | 17.854 | 17.854 | 191.844 |  | 30.27 | 30.27 | 222.114 |  |  | 0 | 222.114
138 | Tamil Nadu | SR | TAN TRANSCO | Supply, Erection, Testing & Commissioning of 1 Nos. of 400kV, 125 MVAR Bus reactor with associated equipments for MPTS Stage III GIS switchyard under total turnkey contract in Erode Region of Tamilnadu. (205) | 2018-01-29 | 12.73 | 2018-10-30 | 2018-11-15 | 10.6 | 5.1 (b) | 90 | 2019-03-13 | 9.54 | 2019-01-07 | 2019-05-24 | 2020-01-22 | 8 | 2020-06-23 | 2021-02-23 |  |  |  |  | 166.378 | 150 | 222.712 | 372.712 | 539.09 |  | 32.6 | 32.6 | 571.69 | 5.95 |  | 5.95 | 577.64
139 | Odisha | ER | OPTCL | Protection Upgradation and installation of Substation Automatic System (SAS) for seven nos of 220/132/33kV Substations (Balasore, Bidanasi, Budhipadar, Katapali, Narendrapur, New-Bolangir & Paradeep). (209) | 2018-03-12 | 41.1 | 2018-10-30 | 2018-11-15 | 40.7 | 5.1 (c) | 90 | 2019-03-13 | 36.63 | 2019-01-07 | 2019-05-24 | 2019-12-18 | 18 | 2020-02-13 | 2021-08-13 |  |  |  |  | 0 | 0 | 2889 | 2889 | 2889 |  | 0 | 0 | 2889 |  |  | 0 | 2889
140 | West Bengal | ER | WBSETCL | Project for establishment of reliable communication and data acquisition at different substation at WBSETCL. (222) | 2018-05-10 | 80.39 | 2018-10-30 | 2018-11-15 | 62.39 | 5.1 (c) | 50 | 2019-03-13 | 31.19 | 2019-01-07 | 2019-05-24 | 2019-06-24 | 25 | 2019-10-23 | 2021-11-23 |  |  |  |  | 37.804 | 0 | 295.064 | 295.064 | 332.868 |  | 42.078 | 42.078 | 374.946 |  |  | 0 | 374.946
141 | Andhra Pradesh | SR | APGENCO | Project on Installation of 1 No. 400kV 125MVAR Bus Reactor in existing 400kV Switchyard at Dr. NTTPS. (243) | 2018-08-20 | 12.95 | 2018-10-30 | 2018-11-15 | 12.41 | 5.1 (b) | 90 | NA | 11.17 | 2019-01-07 | 2020-12-17 |  | 13
142 | Karnataka | SR | KPTCL | Implementation of Integated system for Scheduling, Accounting, Metering and Settlement of Transactions (SAMAST) system in SLDC Karnataka. (195) | 2017-12-22 | 43.34 | 2019-03-25 | 2019-07-26 | 10 | 5.1(c ) | 90 | NA | 9 | 2020-01-31 | 2020-03-20 | 2020-06-22 | 12 | 2020-11-06 | 2021-11-06
143 | West Bengal | ER | WBSETCL | Implementation of Integated system for Scheduling, Accounting, Metering and Settlement of Transactions (SAMAST) system in West Bengal. (197) | 2017-12-22 | 25.96 | 2019-03-25 | 2019-07-26 | 11.2 | 5.1(c ) | 90 | NA | 10.08 | 2020-01-31 | 2020-03-20 | 2020-06-22 | 12
144 | Bihar | ER | BSPTCL | Implementation of Schedulling, Accounting, Metering and settlement of Transcation in Electricity (SAMAST)in SLDC Bihar.(208) | 2018-02-27 | 93.76 | 2019-03-25 | 2019-07-26 | 7.61 | 5.1(c ) | 90 | NA | 6.85 | 2020-01-31 | 2020-03-20 |  | 12
145 | Haryana | NR | HVPN | Implementation of SAMAST (scheduling, Accounting, Meeting and Settement of Transactions in Electricity) in Haryana. (212) | 2018-03-21 | 32.94 | 2019-03-25 | 2019-07-26 | 17.91 | 5.1(c ) | 90 | NA | 16.12 | 2020-01-31 | 2020-03-20 | 2020-06-16 | 12
146 | Punjab | NR | PSTCL | Projects of Implementations of SAMAST (Scheduling, Accounting, Metering & Settlement of Transactions in Electricity) report in the State of Punjab. (255) | 2018-11-19 | 32.64 | 2019-03-25 | 2019-07-26 | 13.58 | 5.1(c ) | 90 | NA | 12.22 | 2020-01-31 | 2020-03-20 | 2020-06-22 | 12 | 2020-10-07 | 2021-10-07
147 | Assam | NER | AEGCL | Implementation of Scheduling, Accounting, Metering & Settlement of Transactions in electricity (SAMAST) of Assam. (231) | 2018-05-31 | 18.53 | 2019-03-25 | 2019-07-26 | 10.25 | 5.1(e ) | 100 | NA | 10.25 | 2020-01-31 | 2020-03-20 | 2020-09-30 | 12 | 2020-11-27 | 2021-11-27
148 | Meghalaya | NER | MePTCL | Implementation of Scheduling, Accounting, Metering & Settlement of Transactions in electricity (SAMAST) of Meghalaya. (232) | 2018-05-31 | 18.77 | 2019-03-25 | 2019-07-26 | 8.48 | 5.1(e ) | 100 | NA | 8.48 | 2020-01-31 | 2020-03-20 | 2020-09-14 | 12 | 2020-11-16 | 2021-11-16
149 | Himachal Pradesh | NR | HPLDA | Implementation of recommendations of SAMAST (Scheduling, Accounting, Metering, and Settlement of Transactions in Electricity) report in the State of Himachal Pradesh. (248) | 2018-10-08 | 15.45 | 2019-03-25 | 2019-07-26 | 8.11 | 5.1(e ) | 100 | NA | 8.11 | 2020-01-31 | 2020-03-20 | 2020-06-22 | 6 | 2020-07-27 | 2021-01-27
150 | Manipur | NER | MSPCL | Installation of Reactive Power Solution on 33/11kV Substation in Manipur. (204) | 2018-01-12 | 56.81 | 2019-05-28 | 2019-07-26 | 21.77 | 5.1(e ) | 100 | NA | 21.77 | 2020-01-31 | 2020-03-20 | 2020-06-26 | 36 | 2020-08-26 | 2023-08-26
151 | Uttar Pradesh | NR | DVVNL | Provision of 11kV Auto Switched capacitor bank at various 33/11kV substation of Agra. (254) | 2018-11-09 | 94.6 | 2019-05-28 | 2019-07-26 | 20.66 | 5.1(b ) | 90 | NA | 18.59 | 2020-01-31 | 2020-03-20 | 2020-07-22 | 24
152 | Uttar Pradesh | NR | PVVNL | Provision of 11kV Auto Switched capacitor bank at various 33/11kV substation of Meerut. (257) | 2018-12-10 | 140.436 | 2019-05-28 | 2019-07-26 | 68.95 | 5.1(b ) | 90 | NA | 62.05 | 2020-01-31 | 2020-03-20 | 2020-09-01 | 24
153 | Uttar Pradesh | NR | MVVNL | Provision of 11kV Auto Switched Capacitor bank at various 33/11kV substatiion of Lucknow. (264) | 2018-12-26 | 202.49 | 2019-05-28 | 2019-07-26 | 52.7 | 5.1(b ) | 90 | NA | 47.73 | 2020-01-31 | 2020-03-20 | 2020-09-14 | 24
154 | Tamil Nadu | SR | TAN TRANSCO | Supply, Erection, Testing & Commissioning of 2 Nos. of 400kV, 125 MVAR Bus reactor with associated equipments for 400kV GIS SS at Manali under total turnkey contract in Chennai North Region of Tamilnadu. (198) | 2017-12-22 | 18.77 | 2019-05-28 | 2019-07-26 | 15.9 | 5.1(b ) | 90 | NA | 14.31 | 2020-01-31 | 2020-03-20 | 2020-09-28 | 8
155 | Meghalaya | NER | MePTCL | Replacement of the 400kV, Bus Reator at 400/220/132kV Substations, Killing, Meghalaya. (199) | 2017-12-22 | 6.9 | 2019-05-28 | 2019-07-26 | 6.86 | 5.1(e ) | 100 | NA | 6.86 | 2020-01-31 | 2020-03-20 | 2020-09-14 | 12 | 2020-11-16 | 2021-11-16
156 | Gujarat | WR | GETCO | Providing Wide Area Monitoring System (WAMS) with PMU and comminication at 31 Locations. Analytics software from IIT Mumbai. (206) | 2018-02-07 | 36.98 | 2019-05-28 | 2019-07-26 | 26.85 | 5.1(c ) | 90 | NA | 24.17 | 2020-01-31 | 2020-03-20 | 2020-06-22 | 12
157 | Madhya Pradesh | WR | MPPTCL | Installation of Phasor Measurement Units (PMUs) at strategic lications in Madhya Pradesh and integration of the same with Phasor Data Conecentrator (PDC) installed under URTDSM project. (246) | 2018-09-24 | 17.8 | 2019-05-28 | 2019-07-26 | 17.8 | 5.1(c ) | 90 | NA | 16.02 | 2020-01-31 | 2020-03-20 | 2020-06-29 | 24
158 | Madhya Pradesh | WR | MPPTCL | Installation of ABT compliant meter having facility of 5 minute integration on existing interface points on MPPTCL . (247) | 2018-09-24 | 6.68 | 2019-05-28 | 2019-07-26 | 2.39 | 5.1(c ) | 90 | NA | 2.15 | 2020-01-31 |  |  | 24
159 | Rajasthan | NR | RRVPNL | Renewable Energy Integration-Reactive compensation Element/ Equipments for Reactiv Power Management and Voltage Control for Transmission Grid under Smart Transmission Network and Asset Management System (Part-A2-Sec-1) . (252) | 2018-10-22 | 113.12 | 2019-05-28 | 2019-07-26 | 63.71 | 5.1(b ) | 90 | NA | 57.34 | 2020-01-31 | 2020-03-20 | 2020-06-22 | 24
160 | Punjab | NR | PSTCL | Design, Testing, Manufacture supply and stringing of HTLS conductor along with replacement of ACSR Zebra/Panther to proide refief to the over-loaded lines. (211) | 2018-03-14 | 7.46 | 2019-05-28 | 2019-07-26 | 7.46 | 5.1(d) | 75 | NA | 5.59 | 2020-01-31 | 2020-03-20 | 2020-06-22 | 7 | 2020-09-24 | 2021-04-24
|  |  | IV: Total; VI: 21447.5027; IX: 17174.79; XIII: 11650.95 | [7 empty] | 1327.7 | 567.4486 | 4185.2826 | 4752.7312 | 6080.4312 | 0 | 1293.6583 | 1293.6583 | 7374.0895 | 57.1278 | 25.764 | 82.8918 | 7456.9812
Note on A4: Author: Provision for filter to be giveg based on Project ID, Category , Region , entity

## Payment Dashboard-3
Project Details | [5 empty] | 10% Stage-1 |  | 20% Stage -2 Payment release details | [10 empty] | 60% Stage -3 Payment release details | [10 empty] | 10% Stage -4 Payment release details | [10 empty] | Total Payment released
Project ID | Name of Scheme and Unique ID No | Category of Funding | Region | State /Entity | Entity | 10% Date | 10% Amount | 1st Tranch Date | 1st Tranch Amount | 2nd Tranch Date | 2nd Tranch Amount | 3rd Tranch Date | 3rd Tranch Amount | 4th Tranch Date | 4th Tranch Amount | 5th Tranch Date | 5th Tranch Amount | Total | 1st Tranch Date | 1st Tranch Amount | 2nd Tranch Date | 2nd Tranch Amount | 3rd Tranch Date | 3rd Tranch Amount | 4th Tranch Date | 4th Tranch Amount | 5th Tranch Date | 5th Tranch Amount | Total | 1st Tranch Date | 1st Tranch Amount | 2nd Tranch Date | 2nd Tranch Amount | 3rd Tranch Date | 3rd Tranch Amount | 4th Tranch Date | 4th Tranch Amount | 5th Tranch Date | 5th Tranch Amount | Total
2 | Renovation and Upgradation of protection system of substations (002) | 5.1(c) | SR | Kerala | KSEBL
3 | Renovation and Upgradation of protection system of substations (003) | 5.1(c) | NR | Rajasthan | RRVPNL
5 | Installation of Bus Reactors (005) | 5.1(b) | NR | Rajasthan | RRVPNL
7 | Renovation and Upgradation of protection system of substations (007) | 5.1(c) | ER | West Bengal | WBSETCL
8 | Renovation and Upgradation of protection system of substaions (008) | 5.1(c) | ER | Odisha | OPTCL
9 | Renovation and Upgradation of protection system of substations(009) | 5.1(c) | SR | Andhra Pradesh | APTRANSCO
10 | Renovation and Upgradation of protection system of substations (010) | 5.1(c) | SR | Andhra Pradesh | APGENCO
11 | Renovation and Upgradation of protection system of substations(011) | 5.1(c) | NER | Assam | AEGCL
12 | Renovation and Upgradation of protection system of substations (12) | 5.1(c) | SR | Karnataka | KPTCL
14 | Renovation and Upgradation of protection system of substations (014) | 5.1(c) | SR | Telangana | TSGENCO
15 | Renovation and Upgradation of protection system of substations (015) | 5.1(c) | SR | Karnataka | KPCL
16 | Renovation and Upgradation of protection system of substations. (016) | 5.1(c) | SR | Telangana | TSTRANSCO
17 | Renovation and Upgradation of protection system of substations (017) | 5.1(c) | NER | Nagaland | DOP, Nagaland
18 | Renovation and Upgradation of protection system of substations (018) | 5.1(c) | ER | Bihar | BSPTCL
20 | Renovation and Upgradation of protection system of substations (020) | 5.1(c) | SR | TamilNadu | TANTRANSCO
21 | Renovation and Upgradation of protection system of substations (021) | 5.1(c) | SR | Puducherry | DoP, Puducherry
23 | Renovation and Upgradation of protection system of substations in Jammu(023) | 5.1(c) | NR | Jammu & Kashmir | PDD-J&K
24 | Renovation and Upgradation of protection system of substations in Kashmir(024) | 5.1(c) | NR | Jammu & Kashmir | PDD-J&K
25 | Installation of Capacitors and FSC. (025) | 5.1(b) | NR | Uttar Pradesh | UPPTCL
26 | Renovation and Upgradation of protection system of substations. (026) | 5.1(c) | NR | Uttar Pradesh | UPPTCL
27 | Reconductoring of existing line by HTLS conductor for relieving congestion. (027) | 5.1(d) | NR | Uttar Pradesh | UPPTCL
28 | Renovation and Upgradation of protection system of substations (28) | 5.1(c) | WR | Madhya Pradesh | MPPTCL
29 | Renovation and Upgradation of protection system of substations.(029) | 5.1(c) | WR | Madhya Pradesh | MPPGCL
32 | Renovation and Upgardation of protection system of substations. (32) | 5.1(c) | NER | Mizoram | DoP, Mizoram
34 | Automatic Demand Management Scheme. (034) | 5.1(c) | WR | Gujarat | GETCO
35 | Load Forecasting Scheme (035) | 5.1(e) | WR | Gujarat | GETCO
38 | Renovation and Upgradation of protection system of substations. (038) | 5.1(c) | NR | BBMB | BBMB
39 | Renovation and Upgradation of protection system. (039) | 5.1(c) | WR | Chhattisgarh | CSPTCL
40 | Renovation and Upgradation of Protection System (040) | 5.1(c) | NER | Tripura | TSEBL
42 | Renovation and Upgardation of protection system of substations (042) | 5.1(c) | NER | Meghalaya | MePTCL
43 | 220kV Super conducting fault current limiter (SCFCL) project (043) | 5.1(c) | WR | Gujarat | GETCO
44 | Renovation and Upgradation of Protection System. (044) | 5.1(c) | NER | Arunachal Pradesh | APPCL
47 | Installation of BCU. (047) | 5.1(c) | NER | Assam | AEGCL
48 | Renovation and Upgradation of Protection System (048) | 5.1(c) | NR | Himachal Pradesh | HPSEBL
49 | Renovation and Upgradation of Protection System.(049) | 5.1(c) | NR | Delhi | DTL
50 | Installation of capacitor banks for reactive power compensation system on 11kV feeders. (50) | 5.1(b) | WR | Gujarat | MGVCL
51 | Renovation and Upgradation of Protection System.(051) | 5.1(c) | NR | Uttrakhand | PTCUL
52 | Bus bar protection (052) | 5.1(c) | NR | Punjab | PSTCL
53 | Installation of capacitor banks for reactive power compensation system on 11kV feeders. (53) | 5.1(b) | WR | Gujarat | UGVCL
54 | Study Program on the integration of renewable energy resources (054) | 5.1(e) | NR | NRPC | NRPC
55 | Renovation and Upgradation of Grid Substation of MSPCL (055) | 5.1(c) | NER | Manipur | MSPCL
56 | Installation of STATCOMs in ER at Ranchi-New, Rourkela, Kishanganj and Jeypore substations of POWERGRID (056) | 5.1(b) | ER | POWERGRID | POWERGRID
57 | Renovation and upgradation of Protection and Contro;l System. (57) | 5.1(c) | NER | Meghalaya | MePGCL
58 | Wind Generation forecasting for state of Gujarat(58) | 5.1(e) | WR | Gujarat | GETCO
59 | Installation of 5 nos. of 125MVAR at 400kV Mahaboobnagar, Mamidipally, Malkaram, Gajwel and Shankarpalli (059) | 5.1(b) | SR | Telangana | TSTRANSCO
61 | Implementation of Integrated system for ABT Open Access and MIS for MPSLDC (061) | 5.1(c) | WR | Madhya Pradesh | MP SLDC
62 | Installation of 125MVAR Bus Reactor at SSTPP Khandwa substation of MPPGCL (062) | 5.1(b) | WR | Madhya Pradesh | MPPGCL
67 | Creation and Maintenance of web based protection database management (067) | 5.1(e) | ER | ERPC | ERPC
70 | Provision of second DC Source at 220KV & 132KV Grid Sub Station of PSTCL. (70) | 5.1(c) | NR | Punjab | PSTCL
71 | Installation of capacitor banks for reactive power compensation system on 11kV feeders. (71) | 5.1(b) | WR | Gujarat | DGVCL
72 | Renovation and Modernization of 220/ 132 kV STPS switch yard and implementation of Substaion Automation System.(072) | 5.1(c) | ER | West Bengal | WBPDCL
73 | Renovation and Upgradation of the protection and control system of 12nos 132/33 Grid Sub Station. (73) | 5.1(c) | ER | Bihar | BSPTCL
74 | Installation of Capacitor bank in 20 Nos of Grid Sub Station (074) | 5.1(b) | ER | Bihar | BSPTCL
75 | Installation of STATCOM in SR region at Hydrabad, Udumalpet & Trichy substations of Powergrid. (75) | 5.1(b) | SR | POWERGRID | POWERGRID
77 | Renovation and modernisation of distribution system of DHBVN, Haryana(077) | 5.1(d) | NR | Haryana | DHVBN
78 | Study programme on the Integration of Renewables Enery Resources (RES) into the Grid. (78) | 5.1(e) | SR | SRPC | SRPC
79 | Procurement Web based management software and protection setting calculation tool. (79) | 5.1(e) | SR | SRPC | SRPC
80 | Implementation of Automatic Demand Management Scheme (ADMS) at 322 Substations of KSEBL at 33kV level. (80) | 5.1(c) | SR | Kerala | KSEBL
81 | Renovation and Upgradation of the protection and control system of Ramgarh Sub Station. (081) | 5.1(c) | ER | DVC | DVC
84 | Renovation and Modernisation of Protection System of 400kV, 230kV & 110kV hydro Generating Stations. (084) | 5.1(c) | SR | Tamilnadu | TANTRANSCO
85 | Establishment of Technical and IT infrastructure for implementation of intra state ABT in Tamilnadu. (085) | 5.1(c) | SR | Tamilnadu | TANTRANSCO
86 | Installation of Capacitor Banks at HV & EHV level at various EHV subatations under Nashik & Pune zones in MSETCL. (086) | 5.1(b) | WR | Maharashtra | MSETCL
87 | Renovation & Modernisation of Transmission System for relieving congestion in intra state transmission system by capacity enhancement of existing network. (087) | 5.1(d) | ER | West Bengal | WBSETCL
88 | Installation of switchable reactor & shunt capacitor for voltage improvement. (88) | 5.1(b) | ER | West Bengal | WBSETCL
89 | Replacement of existing ACSR conductor by HTLS conductor for reliving congestion. (89) | 5.1(d) | NR | Uttar Pradesh | UPPTCL
90 | Construction of Madakkathara – Areakode 400/220kV Multi-circuit Multi-voltage transmission Line (95km) & Construction of Kizhisseri-Nallalam 220/110kV Multi-Circuit Multi Voltage transmission line. (090) | 5.1(c) | SR | Kerala | KSEBL
93 | 33kV system Integration with SLDC system in manipur. (093) | 5.1(c) | NER | Manipur | Manipur SLDC
94 | Funding of BNC Agra HVDC (94) | 4(3)(A) | Central | POWERGRID | POWERGRID
96 | Up-rating Kakkayam - Nallalam 110kV line (45km) & Upgrading Nallalam- Chevayur-Westhill-Koyilandy110kV Single Circuit line in to Double Circuit line.(96) | 5.1(d) | SR | Kerala | KSEBL
97 | Implementation of Islanding scheme at Bandel Thermal Power Station. (097) | 5.1(c) | ER | West Bengal | WBPDCL
98 | Replacement of existing 0.15 ACSR wolf conductor of 132kV Balapur-Patur-Malegoan corridor by High Ampacity Conductor. (098) | 5.1(d) | WR | Maharashtra | MSETCL
99 | Replacement of existing 0.2 ACSR wolf conductor of 132kV Khapri-Besa (Nagpur Ring Main Line) High Ampacity Conductor. (099) | 5.1(d) | WR | Maharashtra | MSETCL
100 | Installation of Shunt Bus Reactors at 400KV Solapur, 400 KV Kolhapur and 400kV Karad substations. (100) | 5.1(b) | WR | Maharashtra | MSETCL
101 | Installation of Shunt Bus Reactors at 400KV Akola, 400 KV Bhusawal-II and 400kV Nanded substations. (101) | 5.1(b) | WR | Maharashtra | MSETCL
102 | Installation of Shunt Bus Reactors at 400KV Koradi, 400 KV Khaparkheda and 400kV Chandrapur-II substations. (102) | 5.1(b) | WR | Maharashtra | MSETCL
103 | Installation of Shunt Bus Reactors at 400KV Lonikand-II, 400 KV Chakan and 400kV Kudus substations. (103) | 5.1(b) | WR | Maharashtra | MSETCL
104 | 75 Nos. RTUs for 132 kv Substations in Maharashtra (104) | 5.1(c) | WR | Maharashtra | MSETCL
106 | Renovation and Modernization of control and protection system and replecement of equipment at Parulia, Durgapur, Kalyanewari, Giridhi Jamsedpur, Barjora, Burnpur, Dhanbad and Bundwan substation. (106) | 5.1(c) | ER | DVC | DVC
109 | Renovation and Upgradation of protection and control system of OHPC. (109) | 5.1(c) | ER | Odisha | OHPCL
110 | "Smart Transmission Operation Management System (STOMS) " in Rajasthan Power System. (110) | 5.1(c) | NR | Rajasthan | RRVPNL
111 | 11kV Rural Feeder Monitoring. (111) | 5.1(e) | Central | RECTPCL | RECTPCL
112 | Implementation of Automatic Demand Management Scheme (ADMS) in the Chhattisfgarh State. (112) | 5.1(c) | WR | Chhattisgarh | CSPTCL
113 | Implementation of ADMS scheme on 33/11kV feeders in Maharashtra. (113) | 5.1(c) | WR | Maharashtra | MSETCL
114 | 30 Nos. of Data Concentrators in MSETCL networks. (114) | 5.1(c) | WR | Maharashtra | MSETCL
117 | Traning Program for Power system Engineers of various constituents of Eastern Region. (117) | 5.1(e) | ER | ERPC | ERPC
118 | Study programme on the Integration of Renewables Energy Resources (RES) into the Grid. (118) | 5.1(e) | NER | NERPC | NERPC
119 | Relieving of Transmission Congestion of existing Overloaded 220kV Lines in Hydrabad city. (119) | 5.1(d) | SR | Telangana | TSTRANSCO
121 | Installation of capacitor banks for reactive power compensation system on 11kV feeders. (121) | 5.1(b) | WR | Gujarat | PGVCL
122 | Study Programme on power trading at NORD POOL Academy for Power System Engineers of Eastern Region. (122) | 5.1(e) | ER | ERPC | ERPC
123 | Installation of : 50 MVAR Line Reactor at 400kV substation at Sarni, Dist. Betul. (123) | 5.1(b) | WR | Madhya Pradesh | MPPGCL
125 | Reliable Communication and data Acquisition System upto 132kV Substation in Chhattisgarh. (125) | 5.1(c) | WR | Chhattisgarh | CSPTCL
126 | Renovation & Up gradation of Various 220 kv switchyard Equipment. (126) | 5.1(c) | SR | Kerala | KSEBL
127 | Project on providing of Reliable communication and Data acquisition system upto 132kV SS. (127) | 5.1(c) | SR | Andhra Pradesh | APTRANSCO
128 | Implementation of OPGW based reliable communication at 132 kv and above substations. (128) | 5.1(c) | ER | Odisha | OPTCL
129 | Implementation of OPGW based reliable communication at 132 kv and above substations. (129) | 5.1(c) | NR | Uttrakhand | PTCUL
134 | Strengthening of Transmission System incidentals to Inter-State- Transmission System in the State of HP (134) | 5.1(d) | NR | Himachal Pradesh | HPSEBL
135 | Reliable Communication and data Acquisition System upto 132kV Substation in Himachal Pradesh (135) | 5.1(c) | NR | Himachal Pradesh | HPSEBL
136 | Communication Backbone "Smart Transmission Network & Asset Management Systeem" Part-B (136) | 5.1(c) | NR | Rajasthan | RRVPNL
137 | Implementation of OPGW based reliable communication at 132 kv and above substations. (137) | 5.1(c) | SR | Telangana | TSTRANSCO
138 | Reliable Communication and data Acquisition System upto 132kV Substation in Punjab. (138) | 5.1(c) | NR | Punjab | PSTCL
140 | Implementation of Automatic Demand Management Scheme (ADMS) Pilot Projects at Three Power Substation in Manipur(140) | 5.1(c) | NER | Manipur | MSPCL
141 | Implementation of OPGW based reliable communication at 132 kv and above substations. (141) | 5.1(c) | SR | Kerala | KSEBL
143 | Implementation of OPGW based reliable communication at 132 kv and above substations. (143) | 5.1(c) | WR | Gujarat | GETCO
144 | Reliable Communication and data Acquisition System upto 132kV Substation in Madhya Pradesh. (144) | 5.1(c) | WR | Madhya Pradesh | MPPTCL
145 | 33/11kV System integration with SLDC System (ADMS) in Nagaland . (145) | 5.1(c) | NER | Nagaland | DOP, Nagaland
146 | Implementation of Automatic Demand Management System (ADMS) to integrate33/11kV System with Arunachal Pradesh SLDC. (146) | 5.1(c) | NER | Arunachal Pradesh | DoP, Arunachal Pradesh
147 | Project on Scheduling, accounting, Meeting and Settlement of Transmission in Electricity (SAMAST) IN Transmission Corporation of Andhra Pradesh (147) | 5.1(c) | SR | Andhra Pradesh | APTRANSCO
148 | 33/11kV System integration with SLDC System Automatic Demand Management Scheme (ADMS) in Mizoram. (148) | 5.1(c) | NER | Mizoram | DOP, Mizoram
149 | Reliable Communication and data Acquisition System upto 132kV Substation in Karnataka. (149) | 5.1(c) | SR | Karnataka | KPTCL
151 | Implementation of OPGW based reliable communication at 132 kv and above substations. (151) | 5.1(c) | SR | Tamilnadu | TANTRANSCO
152 | Implementation of OPGW based reliable communication at 132 kv and above substations. (152) | 5.1(c) | NER | Manipur | MSPCL
153 | Real Time Data Acquisition System for Monitoring & Control of Transmission Grid under STNAMS (PART A-1) (153) | 5.1(c) | NR | Rajasthan | RRVPNL
155 | Renovation and Modernization of switchyard and related protection system of different power stations (BTPS, BKTPS and KTPS) of WBPDCL (155) | 5.1(c) | ER | West Bengal | WBPDCL
156 | 33/11kV System Integration with SLDC System (ADMS) in Assam. (156) | 5.1(c) | NER | Assam | APDCL
158 | Provision of Bus Reactors at 400kV Grid Substations of PSTCL. (158) | 5.1(b) | NR | Punjab | PSTCL
161 | Renovation and Upgradation of protection system of substations. (161) | 5.1(c) | ER | Jharkhand | JUSNL
166 | 33/11kV System integration with SLDC system in (ADMS) Meghalaya. (166) | 5.1(c) | NER | Meghalaya | MePDCL
167 | Installation of 125MVAR Bus Reactor at 400kV Switchyard Sanjay Gandhi TPS, at Substations at Birsinghpur under PSDF. (167) | 5.1(b) | WR | Madhya Pradesh | MPPGCL
173 | Drawing of optical ground wire (OPGW) cables on existing 132kV & 66kV transmission lines and integration of leftover substations with State Load Despatch Centre, Sikkim. (173) | 5.1(c) | ER | Sikkim | ENPD Sikkim
174 | Installation of 125MVAR Bus Reactor at 400kV Switchyard at Shree Singaji TTP Stage-II, Dist: Khandwa. (174) | 5.1(b) | WR | Madhya Pradesh | MPPGCL
177 | Reliable Communication & Data Acquistion System upto 132kV Substaions ER .(177) | 5.1(c) | ER | Jharkhand | JUSNL
179 | Installation of 125 MVAR Bus Reactor along with construction of associated by each at 400kV Grid S/S of Mendhasal, Meramundali & New Duburi for VAR control & stabilisation of system voltage. (179) | 5.1(b) | ER | Odisha | OPTCL
180 | Project on providing of Reliable Communication & Data Acquisition system upto 132kV SS. (180) | 5.1(c) | SR | Puducherry | DoP, Puducherry
186 | Installation of Numerical line differential relays in the 132kV transmission lines. (Short Lines). (186) | 5.1(b) | NER | Meghalaya | MePTCL
188 | Supply, Erection, Testing & Commissioning of 2 Nos. of 400kV, 80 MVAR Bus reactor with associated equipments for 400/230-110 kV AIS SS at Kamudhi under total turnkey cintract cintract in Madurai Region of Tamilnadu. (188) | 5.1(b) | SR | Tamilnadu | TAN TRANSCO
193 | Supply, Erection, Testing & Commissioning of 1 Nos. of 400kV, 125 MVAR Bus reactor with associated equipments for 400/230-110 kV SS at Kayathar under total turnkey contract in Tiruneveli Region of Tamilnadu. (193) | 5.1(b) | SR | Tamilnadu | TAN TRANSCO
195 | Implementation of Integated system for Scheduling, Accounting, Metering and Settlement of Transactions (SAMAST) system in SLDC Karnataka. (195) | 5.1(c) | SR | Karnataka | KPTCL
196 | Implementation of Automatic Demand Management System (ADMS) in SLDC, Odisha. (196) | 5.1(c) | ER | Odisha | OPTCL
197 | Implementation of Integated system for Scheduling, Accounting, Metering and Settlement of Transactions (SAMAST) system in West Bengal. (197) | 5.1(c) | ER | West Bengal | WBSETCL
198 | Supply, Erection, Testing & Commissioning of 2 Nos. of 400kV, 125 MVAR Bus reactor with associated equipments for 400kV GIS SS at Manali under total turnkey contract in Chennai North Region of Tamilnadu. (198) | 5.1(b) | SR | Tamilnadu | TAN TRANSCO
199 | Replacement of the 400kV, Bus Reator at 400/220/132kV Substations, Killing, Meghalaya. (199) | 5.1(e) | NER | Meghalaya | MePTCL
201 | Protection Data base management System. The project will be implemented in following States: Arunachal Pradesh, Assam, Manipur, Meghalaya, Mizoram, Nagaland & Tripura. (201) | 5.1(e) | NER | NERPC | NERPC
202 | Supply, Erection, Testing & Commissioning of 1 Nos. of 400kV, 125 MVAR Bus reactor with associated equipments for 400kV SS at Alamathy under total turnkey contract in Chennai North Region of Tamilnadu. (202) | 5.1(b) | SR | Tamilnadu | TAN TRANSCO
203 | Creation and Maintenance of Web based Protection Database Management and PC based Protection Setting Calculation Tool for Northern Region Power System Network. (203) | 5.1(e) | NR | NRPC | NRPC
204 | Installation of Reactive Power Solution on 33/11kV Substation in Manipur. (204) | 5.1(e) | NER | Manipur | MSPCL
205 | Supply, Erection, Testing & Commissioning of 1 Nos. of 400kV, 125 MVAR Bus reactor with associated equipments for MPTS Stage III GIS switchyard under total turnkey contract in Erode Region of Tamilnadu. (205) | 5.1(b) | SR | Tamilnadu | TAN TRANSCO
206 | Providing Wide Area Monitoring System (WAMS) with PMU and comminication at 31 Locations. Analytics software from IIT Mumbai. (206) | 5.1(c) | WR | Gujarat | GETCO
208 | Implementation of Schedulling, Accounting, Metering and settlement of Transcation in Electricity (SAMAST)in SLDC Bihar.(208) | 5.1(c) | ER | Bihar | BSPTCL
209 | Protection Upgradation and installation of Substation Automatic System (SAS) for seven nos of 220/132/33kV Substations (Balasore, Bidanasi, Budhipadar, Katapali, Narendrapur, New-Bolangir & Paradeep). (209) | 5.1(c) | ER | Odisha | OPTCL
210 | Imstalltion of Bus Reactors at different 400kV Substation within the state of West Bengal for reactive power management of the Grid. (210) | 5.1(b) | ER | West Bengal | WBSETCL
211 | Design, Testing, Manufacture supply and stringing of HTLS conductor along with replacement of ACSR Zebra/Panther to proide refief to the over-loaded lines. (211) | 5.1(d) | NR | Punjab | PSTCL
212 | Implementation of SAMAST (scheduling, Accounting, Meeting and Settement of Transactions in Electricity) in Haryana. (212) | 5.1(c) | NR | Haryana | HVPN
222 | Project for establishment of reliable communication and data acquisition at different substation at WBSETCL. (222) | 5.1(c) | ER | West Bengal | WBSETCL
223 | Installation of 1x25 MVAR, 220kV Bus Reactor each at 400kV GSS Akal, 220kV GSS Suratgarh & 220kV GSS Bikaner. (223) | 5.1(b) | NR | Rajasthan | RRVPNL
224 | Reliable Communiacation System for 132 kV & above network in Haryana. (224) | 5.1(c) | NR | Haryana | HVPN
226 | Implementation of Automatic Demand Management System (ADMS) in SLDC, Tripura. (226) | 5.1(c) | NER | Tripura | TSECL
231 | Implementation of Scheduling, Accounting, Metering & Settlement of Transactions in electricity (SAMAST) of Assam. (231) | 5.1(e) | NER | Assam | AEGCL
232 | Implementation of Scheduling, Accounting, Metering & Settlement of Transactions in electricity (SAMAST) of Meghalaya. (232) | 5.1(e) | NER | Meghalaya | MePTCL
238 | Implementation & Supply of Numerical Line differential as Main-I Protection with inbuilt distance Relays towards Retrofit of existing protection schemes on 400kV lines at various 400kV substations in MSETCL. (238) | 5.1(b) | WR | Maharashtra | MSETCL
239 | Project on commissioning of 125MVAR Bus Reactors on 400kV SS Sattenapalli and 400kV SS Chittoor in Transmission Corporation of Andhra Pradesh. (Part-1) (239) | 5.1(b) | SR | Andhra Pradesh | APTRANSCO
243 | Project on Installation of 1 No. 400kV 125MVAR Bus Reactor in existing 400kV Switchyard at Dr. NTTPS. (243) | 5.1(b) | SR | Andhra Pradesh | APGENCO
246 | Installation of Phasor Measurement Units (PMUs) at strategic lications in Madhya Pradesh and integration of the same with Phasor Data Conecentrator (PDC) installed under URTDSM project. (246) | 5.1(c) | WR | Madhya Pradesh | MPPTCL
247 | Installation of ABT compliant meter having facility of 5 minute integration on existing interface points on MPPTCL . (247) | 5.1(c) | WR | Madhya Pradesh | MPPTCL
248 | Implementation of recommendations of SAMAST (Scheduling, Accounting, Metering, and Settlement of Transactions in Electricity) report in the State of Himachal Pradesh. (248) | 5.1(e) | NR | Himachal Pradesh | HPLDA
252 | Renewable Energy Integration-Reactive compensation Element/ Equipments for Reactiv Power Management and Voltage Control for Transmission Grid under Smart Transmission Network and Asset Management System (Part-A2-Sec-1) . (252) | 5.1(b) | NR | Rajasthan | RRVPNL
254 | Provision of 11kV Auto Switched capacitor bank at various 33/11kV substation of Agra. (254) | 5.1(b) | NR | Uttar Pradesh | DVVNL
255 | Projects of Implementations of SAMAST (Scheduling, Accounting, Metering & Settlement of Transactions in Electricity) report in the State of Punjab. (255) | 5.1(c) | NR | Punjab | PSTCL
257 | Provision of 11kV Auto Switched capacitor bank at various 33/11kV substation of Meerut. (257) | 5.1(b) | NR | Uttar Pradesh | PVVNL
264 | Provision of 11kV Auto Switched Capacitor bank at various 33/11kV substatiion of Lucknow. (264) | 5.1(b) | NR | Uttar Pradesh | MVVNL
0 | 0 | 0 | 0 | 0
Total | 160 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Note on A4: Suhas Dambhare (सुहास धमभरे) Provision for filter to be giveg based on Project ID, Category , Region , entity

## Entity Payment processing modul
Payment processing Module
Entity Screen
Details of LOA placed and Eligible Grant.
Proj ID | Approved Cost | Approved Grant | LOA & Eligible Grant Details
|  |  | LOA No | LOA Value | Eligible Grant Stg-1 (10%) | Claimed Grant | Received Grant | Balance Eligible Grant | Balance Approved Grant
A | B | C | D | E | F=0.1B | K | L | M | N
1 |  |  | 1
2
3
4
5
6
7
8
9
10
Total | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Proj ID | Approved Cost | Approved Grant | STAGE-2 (20%) LOA wise grant claimed
|  |  | LOA No | LOA Value | Eligible Grant Stg-2 (20%) | Tranch-1 | Tranch-2 | Tranch-3 | Tranch-4 | Tranch-5 | Claimed Grant Total | Received Grant Total | Balance Eligible Grant | Balance Approved Grant
A | B | C | D | E | G=0.2E | [5 empty] | K | L | M | N
1 |  |  | 1
2
3
4
5
6
7
8
9
10
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proj ID | Approved Cost | Approved Grant | STAGE-3 (60%) LOA wise grant claimed
|  |  | LOA No | LOA Value | Eligible Grant Stg-2 (20%) | Tranch-1 | Tranch-2 | Tranch-3 | Tranch-4 | Tranch-5 | Claimed Grant Total | Received Grant Total | Balance Eligible Grant | Balance Approved Grant
A | B | C | D | E | G=0.6E | [5 empty] | K | L | M | N
1 | 100 | 90 | 1 | 10 | 5.4 | [7 empty] | 5.4
|  |  | 2 | 10 | 5.4 | [7 empty] | 5.4
|  |  | 3 | 20 | 10.8 | [7 empty] | 10.8
|  |  | 4 | 30 | 16.2 | [7 empty] | 16.2
|  |  | 5 | 5 | 2.7 | [7 empty] | 2.7
|  |  | 6 | 15 | 8.1 | [7 empty] | 8.1
|  |  | 7 | 10 | 5.4 | [7 empty] | 5.4
|  |  | 8 | [9 empty] | 0
|  |  | 9 | [9 empty] | 0
|  |  | 10 | [9 empty] | 0
Total | 100 | 90 |  | 100 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0
Proj ID | Approved Cost | Approved Grant | STAGE-4 (10%) LOA wise grant claimed
|  |  | LOA No | LOA Value | Eligible Grant Stg-4 (20%) | Tranch-1 | Tranch-2 | Tranch-3 | Tranch-4 | Tranch-5 | Claimed Grant Total | Received Grant Total | Balance Eligible Grant | Balance Approved Grant
A | B | C | D | E | G=0.6E | [5 empty] | K | L | M | N
1 | 100 | 90 | 1 | 10 | 5.4
|  |  | 2 | 10 | 5.4
|  |  | 3 | 20 | 10.8
|  |  | 4 | 30 | 16.2
|  |  | 5 | 5 | 2.7
|  |  | 6 | 15 | 8.1
|  |  | 7 | 10 | 5.4
8
9
10
Total | 100 | 90 |  | 100 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Details of stagewise Payment Claimed and Received
Proj ID | Approved Cost | Approved Grant | Stagewise Claim details
|  |  | Stage | Tranch | Eligible Grant | Claimed Grant | Received Grant | Balance grant
A | B | C | D | E | F | G | H | I=F-H | J=C-F
|  |  | Stg-1 (10%) Initial | Tranch-1 | 0 | 10 | 10 | -10
|  |  | Stg-2 (20%) | Tranch-1
Tranch-2
Tranch-3
Tranch-4
Tranch-5
|  |  | Stg-3 (60%) | Tranch-1
Tranch-2
Tranch-3
Tranch-4
Tranch-5
|  |  | Stg-4 (10%) Final | Tranch-1
Tranch-2
Tranch-3
Tranch-4
Tranch-5
Note on G10: Author: click to open LOA uploading module
Note on H10: Author: Data will populate after uploading of LOA BOQ in LOA uploading Module
Note on I10: Author: Data will pupulate based on Approved grant
Note on H26: Author: Data will populate automatically after LOA module is filled up
Note on J26: Author: To be filled up by Entity

## Entity LOA upload module
| Details as per the DPR (scheme) approved for funding from PSDF | [5 empty] | letter of award placed by the entity for the items approved under the scheme
Sr. No. | Item No in the BOQ | Description of item | Qty | Unit Price With Taxes | Cost in Lakhs | Grand Total | Details of theLOA, Vender name, LOA No.and date, delivery/ completion schedule. | Package detail(As per tendering) | LOA-1 |  |  |  |  | Cost As per DPR | Qty Delivered at site (Nos)_20.06.2017 | Qty Delivered at site (Nos) | Processed bill amount |  |  | Paid bill amount |  |  | From F&A utilization | Remarks |  | Balance Quantity | LOA-2 |  |  |  | Cost As per DPR | Qty Delivered at site (Nos)_20.06.2017 | Qty Delivered at site (Nos) | Processed bill amount |  |  | Paid bill amount |  |  | From F&A utilization | Remarks |  | Balance Quantity
[9 empty] | Qty (Nos) | Unit price Rs with taxes |  | Awarded cost Rs. with taxes |  |  |  |  | with taxes | State level taxes | without State Level taxes | Less VAT | Less Retention Money | Net paid | Net paid |  |  |  | Qty (Nos) | Unit price Rs with taxes | Awarded cost Rs. with taxes |  |  |  |  | with taxes | State level taxes | without State Level taxes | Less VAT | Less Retention Money | Net paid | Net paid
1 | 1.01 | 220kV CB (1-pole) | 18 | 1912226.5683 | 34420078.2293 | 70587558.2051 | Hi Tech Corporation, AEGCL/MD/Tech-589/PSDF/CB/220kV/25 dated07.03.2016 | Package A (220kV CB 1-Pole/3-Pole) | 19 | 1898588.5526 | 1812795.5263 | 36073183 | 34443115 | 70587558.2051 | 19 | 10 | 18281490 | 827690 | 17453800 | 993228 | 914074.5 | 16374187.5 | 16374186 |  | #REF! | -1 |  |  |  | 0 | 0 | 19 | 10 | 18281490 | 827690 | 17453800 | 993228 | 914074.5 | 16374187.5 | 16374186 |  | #REF! | 0
| 1.02 | 220kV CB (3-pole) | 18 | 2009304.4431 | 36167479.9758 |  | Hi Tech Corporation, AEGCL/MD/Tech-589/PSDF/CB/220kV/26 dated07.03.2016 | Package B (220kV CB 1-Pole/3-Pole) | 17 | 1932316.4706 | 1845764.7059 | 32849380 | 31378000 |  | 17 | 7 | 12991950 | 582950 | 12409000 | 699540 | 649597.5 | 11642812.5 | 11642811 | Mandatory Spare Items: Closing Coil, Tripping Coil, Spring Charging Motor, SF6 Gas density Motor, Set of all Gasket used sealing agent has not been supplied and shall be supplied along with the second lot. Only CB operating mechanism has been supplied |  | 1 |  |  |  | 0 |  | 17 | 7 | 12991950 | 582950 | 12409000 | 699540 | 649597.5 | 11642812.5 | 11642811 | Mandatory Spare Items: Closing Coil, Tripping Coil, Spring Charging Motor, SF6 Gas density Motor, Set of all Gasket used sealing agent has not been supplied and shall be supplied along with the second lot. Only CB operating mechanism has been supplied |  | 0
132 kV CB | [6 empty] | 132 KV CB | [18 empty] | 0 | [16 empty] | 0
2 | 1.03 | 132 kV (3-Pole) | 119 | 1058678.1796 | 125982703.3692 | 125982703.3692 | Hi Tech Corporation, AEGCL/MD/Tech-590/PSDF/CB/132kV/29 dated07.03.2016 | Package A (132 kV CB) | 41 | 799390.2439 | 763424.1463 | 32775000 | 31300390 | 125982703.3692 | 41 | 41 | 31314710 | 1413510 | 29901200 | 1696212 | 1565735.5 | 28052763 | 28052757 |  |  | 78 |  |  |  | 0 | 0 | 41 | 41 | 31314710 | 1413510 | 29901200 | 1696212 | 1565735.5 | 28052763 | 28052757 |  |  | 0
[7 empty] | Hi Tech Corporation, AEGCL/MD/Tech-590/PSDF/CB/132kV/30 dated07.03.2016 | Package B (132 kV CB) | 41 | 808201.7073 | 771754.6341 | 33136270 | 31641940 |  | 41 | 41 | 31592330 | 1462030 | 30130300 | 1715676 | 1579616.5 | 28297037.5 | 28297032 |  |  | -41 |  |  |  | 0 |  | 41 | 41 | 31592330 | 1462030 | 30130300 | 1715676 | 1579616.5 | 28297037.5 | 28297032 |  |  | 0
[7 empty] | Hi Tech Corporation, AEGCL/MD/Tech-590/PSDF/CB/132kV/31 dated07.03.2016 | Package C (132 kV CB) | 37 | 801807.8378 | 765913.5135 | 29666890 | 28338800 |  | 37 | 37 | 27511590 | 1235790 | 26275800 | 1482948 | 1375579.5 | 24653062.5 | 24653058 |  |  | -37 |  |  |  | 0 |  | 37 | 37 | 27511590 | 1235790 | 26275800 | 1482948 | 1375579.5 | 24653062.5 | 24653058 |  |  | 0
66kV & 33kV CB | [6 empty] | 66kV, 33kV CB | [18 empty] | 0 | [16 empty] | 0
3 | 1.04 | 66 kV CB | 21 | 750410.321 | 15758616.7408 | 111988240.0177 | Hi Tech Corporation, AEGCL/MD/Tech-591/PSDF/CB/66 & 33 kV/20 dated07.03.2016 | Package D (66 kV CB) | 19 | 691484.8158 | 660148.2368 | 13138211.5 | 12542816.5 | 111988240.0177 | 19 | 19 | 12603210 | 573010 | 12030200 | 687612 | 630160.5 | 11285437.5 | 11285437 |  |  | 2 |  |  |  | 0 | 0 | 19 | 19 | 12603210 | 573010 | 12030200 | 687612 | 630160.5 | 11285437.5 | 11285437 |  |  | 0
| 1.05 | 33 kV CB | 143 | 672934.4285 | 96229623.2769 |  | Hi Tech Corporation, AEGCL/MD/Tech-591/PSDF/CB/66 & 33 kV/17 dated07.03.2016 | Package A (33 kV CB) | 52 | 439502.5962 | 419517.4038 | 22854135 | 21814905 |  | 52 | 30 | 12413220 | 566820 | 11846400 | 680184 | 620661 | 11112375 | 11112375 |  |  | 91 |  |  |  | 0 |  | 52 | 30 | 12413220 | 566820 | 11846400 | 680184 | 620661 | 11112375 | 11112375 |  |  | 0
[7 empty] | Hi Tech Corporation, AEGCL/MD/Tech-591/PSDF/CB/66 & 33 kV/18 dated07.03.2016 | Package B (33 kV CB) | 47 | 438019.3617 | 418152.1277 | 20586910 | 19653150 |  | 47 | 27 | 11153160 | 507960 | 10645200 | 609552 | 557658 | 9985950 | 9985950 |  |  | -47 |  |  |  | 0 |  | 47 | 27 | 11153160 | 507960 | 10645200 | 609552 | 557658 | 9985950 | 9985950 |  |  | 0
[7 empty] | Hi Tech Corporation, AEGCL/MD/Tech-591/PSDF/CB/66 & 33 kV/19 dated07.03.2016 | Package C (33 kV CB) | 44 | 442187.8409 | 422173.9773 | 19456265 | 18575655 |  | 44 | 44 | 18405860 | 836660 | 17569200 | 1003992 | 920293 | 16481575 | 16481575 |  |  | -44 |  |  |  | 0 |  | 44 | 44 | 18405860 | 836660 | 17569200 | 1003992 | 920293 | 16481575 | 16481575 |  |  | 0
Total | [6 empty] | Total |  |  |  |  | 240536244.5 | 10 |  |  |  | 176267520 |  | 168261100 | 9568944 |  | 157885200.5 | 157885181 | [6 empty] | 10 |  |  |  | 176267520 |  | 168261100 | 9568944 |  | 157885200.5 | 157885181
[16 empty] | 115 | [16 empty] | 115
[16 empty] | 98 | [16 empty] | 98
Note on B2: Author: already filled up by Admin as per approved BOA
Note on K3: Author: To be filled by Entity as per LOA BOQ
Note on AJ3: Author: To be filled by Entity as per LOA BOQ
Note on N17: Author: This value will automatically populated in Payment Processing module
Note on AM17: Author: This value will automatically populated in Payment Processing module